## Sheet2
Overall Project Distribution
Layer | Member 1 | Member 2 | Member 3 | Member 4
| Grishma | Malin | Nanda | ALL
Frontend | Authentication & Dashboard | Student & Parent Management | Faculty, Attendance & Timetable | Fees, Reports & Admin
Backend | Authentication, Users & Institute APIs | Student, Course & Batch APIs | Faculty, Attendance & Academic APIs | Fee, Exam, Reports & Notification APIs
Database | Core System Collections | Student Collections | Faculty Collections | Finance & Report Collections
Frontend Taks Assignment
Member | Module | Pages | Components | API Integration | Priority
Member 1 | Authentication & Dashboard | 15+ | Login, Register, Forgot Password, Dashboard Cards, Sidebar, Navbar, Profile | Auth APIs | High
Member 2 | Student & Parent Management | 18+ | Student CRUD, Parent Portal, Admission, Profile, Search, Tables | Student APIs | High
Member 3 | Faculty, Attendance & Timetable | 17+ | Faculty CRUD, Attendance, Timetable, Batch, Course | Attendance APIs | High
Member 4 | Fees, Exams, Reports & Admin | 20+ | Fee, Payment, Reports, Analytics, Settings | Fee APIs | High
Backend Task Assignment
Member | Module | APIs | Responsibilities | Priority
Member 1 | Authentication, User Management & Institute Management | 25+ APIs | Login, Register, JWT Authentication, RBAC, Users, Roles, Permissions, Institute, Branch, Academic Year, Holidays, System Settings | High
Member 2 | Student, Parent, Course & Batch Management | 30+ APIs | Student CRUD, Parent Management, Admission, Course Management, Subject Management, Batch Management, Enrollment, Student Documents | High
Member 3 | Faculty, Attendance & Academic Management | 28+ APIs | Faculty CRUD, Attendance (Manual, Face, Fingerprint), Timetable, Assignments, Homework, Study Materials | High
Member 4 | Fee, Examination, Reports & Administration | 32+ APIs | Fee Management, Payments, Examinations, Results, Report Cards, Notifications, Dashboard, Analytics, Audit Logs | High
Database Architecture Assignment
Member | Module | Collections | Database Responsibilities | Priority
Member 1 | Core System & Authentication | 11 Collections | Users, Roles, Permissions, Sessions, OTP, Institutes, Branches, Academic Years, Holidays, System Settings, Login History | High
Member 2 | Student & Academic Management | 10 Collections | Students, Parents, Courses, Subjects, Batches, Enrollments, Student Documents, Admission Applications, Transfer History, Activity Logs | High
Member 3 | Faculty & Academic Operations | 10 Collections | Faculties, Faculty Assignments, Timetables, Attendance, Attendance Corrections, Assignments, Assignment Submissions, Homework, Study Materials, Attendance Analytics | High
Member 4 | Finance & Administration | 12 Collections | Fee Structures, Student Fees, Payments, Refund Requests, Examinations, Student Results, Report Cards, Notifications, Announcements, Reports, Dashboard Analytics, Audit Logs | High
# Pull latest changes |  |  | # Get the latest branches
git pull origin main |  |  | git fetch origin
# Create a new branch |  |  | # Switch to the developer's branch
git checkout -b feature/login-page |  |  | git checkout frontend/login-page
# Make your code changes |  |  | # Install dependencies
npm install
# Stage files
git add . |  |  | # Start the project
npm run dev
# Commit
git commit -m "Added login page" |  |  | # (Test the feature manually)
# Push the branch |  |  | # Return to main after review
git push origin feature/login-page |  |  | git checkout main
git pull origin main
Step 1: Open the Pull Request
On GitHub:
1. Go to your repository.
2. Click Pull requests.
3. Open the PR submitted by your team member.
Check:
· PR title
· Description
· Files changed
· Number of commits
Step 2: Review the Changed Files
Open the Files changed tab.
Check for:
· Correct logic
· Clean code
· Proper indentation
· Meaningful variable names
· No unnecessary files
· No commented-out code
· No secrets (API keys, passwords, .env files)
Example comments:
· ✅ "Good implementation."
· ⚠️ "Please rename this variable to something more descriptive."
· ⚠️ "This function is too long. Consider splitting it."
Step 3: Review the Code Locally (Recommended)
Instead of reviewing only on GitHub, test the code on your own machine.
Option 1: Fetch the contributor's branch
git fetch origin
See all branches:
git branch -r
Example output:
origin/main
origin/frontend/login-page
origin/backend/auth-api
Switch to the branch:
git checkout frontend/login-page
Or, if you don't have it locally:
git checkout -b frontend/login-page origin/frontend/login-page
Step 4: Install Dependencies
Frontend:
npm install
Backend:
npm install
Python backend (if applicable):
pip install -r requirements.txt
Step 5: Run the Project
Frontend:
npm run dev
Backend:
npm start
or
npm run dev
Step 6: Test the Feature
If the PR adds a login page:
· Does the page load?
· Are there any console errors?
· Is the UI responsive?
· Does form validation work?
· Are buttons functional?
· Does it integrate correctly with the backend?
If it's a backend feature:
· Test the API using Postman or another API client.
· Check database operations.
· Verify error handling.
Step 7: Check the Browser Console
Press F12 and look for:
· JavaScript errors
· Warnings
· Failed network requests
Step 8: Check the Terminal
Look for:
· Runtime errors
· Build errors
· Dependency issues
Step 9: Run Automated Checks (if available)
If your project has scripts:
npm test
npm run lint
npm run build
These help catch errors before merging.
Step 10: Review the Git Changes
View the commit history:
git log --oneline
See exactly what changed:
git diff main..frontend/login-page
Step 11: Check Project Standards
Ask yourself:
· Is the code readable?
· Does it follow the project's folder structure?
· Are components reusable?
· Is there duplicate code?
· Are functions unnecessarily large?
· Are files named consistently?
· Are unnecessary console.log() statements removed?
Step 12: Decide the Outcome
Approve
If everything looks good:
· Click Review changes
· Select Approve
· Submit the review
Request Changes
If issues are found:
· Click Review changes
· Select Request changes
· Add comments explaining what needs to be fixed
Comment
If you only have suggestions:
· Select Comment
· Leave your feedback without blocking the merge
Step 13: Merge the Pull Request
After approval:
1. Click Merge pull request
2. Click Confirm merge
3. Delete the feature branch if it's no longer needed

## M1 grishma
Team Member 1 – Frontend Task Assignment
Role: Frontend Developer (Authentication & Core UI) |  |  |  | Grishma
Technology Stack
· React.js
· TypeScript
· Tailwind CSS
· React Router DOM
· Axios
· React Hook Form
· JWT Authentication
· Context API / Redux (if required)
Sprint 1 - Project Setup |  |  |  |  | Sprint 2 - Authentication Module |  |  |  |  | Sprint 3 - Dashboard Layout |  |  |  |  | Sprint 4 - Dashboard Home |  |  |  |  | Sprint 5 - User Profile |  |  |  |  | Sprint 6 - Common Components |  |  |  |  | Sprint 7 - Error Handling |  |  |  |  | Sprint 8 - Responsive Design
Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status
FE-001 | Project Setup | Configure React + TypeScript + Tailwind CSS project structure and install required dependencies. | High | Pending | FE-005 | Login Page | Design responsive login page with Email/Mobile/Username and Password fields. | High | Pending | FE-012 | Dashboard Layout | Create reusable dashboard layout for all modules. | High | Pending | FE-017 | Dashboard Cards | Display total students, faculty, courses, attendance, and revenue summary cards. | High | Pending | FE-022 | Profile Page | Display logged-in user's personal information and role details. | High | Pending | FE-026 | Button Component | Create reusable button component with variants. | High | Pending | FE-033 | 404 Page | Design custom page-not-found screen. | Low | Pending | FE-037 | Mobile Optimization | Ensure all pages work correctly on mobile devices. | High | Pending
FE-002 | Folder Structure | Create scalable folder structure (pages, components, layouts, services, hooks, utils). | High | Pending | FE-006 | Forgot Password | Create forgot password page with OTP request form. | High | Pending | FE-013 | Sidebar | Develop collapsible responsive sidebar with role-based navigation. | High | Pending | FE-018 | Quick Actions | Add shortcut buttons for common operations like Add Student and Add Course. | Medium | Pending | FE-023 | Edit Profile | Allow users to update profile information and profile picture. | Medium | Pending | FE-027 | Input Component | Develop reusable input fields with validation states. | High | Pending | FE-034 | 403 Page | Create unauthorized access page. | Low | Pending | FE-038 | Tablet Optimization | Optimize layout for tablet screen sizes. | Medium | Pending
FE-003 | Routing Setup | Configure React Router with protected and public routes. | High | Pending | FE-007 | OTP Verification | Design OTP verification screen with resend timer and validation. | High | Pending | FE-014 | Navbar | Build top navigation bar with institute logo, search, notifications, and profile. | High | Pending | FE-019 | Recent Activities | Show latest system activities in a timeline. | Medium | Pending | FE-024 | Change Password | Provide secure password update functionality. | High | Pending | FE-028 | Card Component | Build reusable card component for dashboard widgets. | High | Pending | FE-035 | 500 Page | Create internal server error page. | Low | Pending | FE-039 | Cross-Browser Testing | Verify UI on Chrome, Edge, Firefox, and Safari. | Medium | Pending
FE-004 | Global Theme | Configure colors, typography, spacing, and responsive breakpoints. | High | Pending | FE-008 | Reset Password | Create reset password page with password strength validation. | High | Pending | FE-015 | Breadcrumb | Display current page navigation path dynamically. | Medium | Pending | FE-020 | Notification Widget | Display recent notifications with unread indicators. | Medium | Pending | FE-025 | Profile Image Upload | Implement profile image upload with preview. | Medium | Pending | FE-029 | Modal Component | Create reusable modal dialog component. | Medium | Pending | FE-036 | Error Boundary | Prevent application crashes by handling React rendering errors. | Medium | Pending
[5 empty] | FE-009 | Session Management | Store JWT token securely and manage login/logout sessions. | High | Pending | FE-016 | Footer | Design reusable footer component. | Low | Pending | FE-021 | Calendar Widget | Integrate calendar showing events, holidays, and exams. | Medium | Pendin | [5 empty] | FE-030 | Toast Notifications | Display success, warning, and error messages. | Medium | Pending
[5 empty] | FE-010 | Protected Routes | Restrict pages based on authentication status. | High | Pending | [15 empty] | FE-031 | Loader | Build loading spinner and skeleton loading components. | Medium | Pending
[5 empty] | FE-011 | Logout Feature | Implement logout functionality and clear session data. | High | Pending | [15 empty] | FE-032 | Empty State | Create reusable empty-state component for tables and pages. | Low | Pending
Backend Task Assignment Role: Backend Developer (Authentication, User Management & Core Infrastructure) Technology Stack 1. Node.js 2. Express.js 3. TypeScript 4. MongoDB (Mongoose) 5. JWT Authentication 6. Bcrypt 7. Nodemailer 8. Redis (Optional) 9. Cloudinary (Profile Images) 10. Multer 11. Express Validator 12. Winston Logger
Sprint 1 - Project Setup & Backend Architecture |  |  |  |  | Sprint 2 - Authentication Module |  |  |  |  | Sprint 3 - Role-Based Access Control (RBAC) |  |  |  |  | Sprint 4 - User Management |  |  |  |  | Sprint 5 - Institute & Branch Management |  |  |  |  | Sprint 6 - File Upload & Cloud Storage |  |  |  |  | Sprint 7 - Security & Middleware |  |  |  |  | Sprint 8 - API Documentation & Testing
Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status
BE1-001 | Backend Setup | Initialize Express + TypeScript project with scalable folder structure. | High | Pending | BE1-007 | User Registration API | Develop secure user registration endpoint. | High | Pending | BE1-015 | Role Management | Create Role schema and CRUD APIs. | High | Pending | BE1-020 | User CRUD APIs | Develop Create, Read, Update, Delete APIs for users. | High | Pending | BE1-026 | Institute CRUD APIs | Create APIs for institute profile management. | High | Pending | BE1-031 | Profile Image Upload | Upload and manage user profile images using Cloudinary. | High | Pending | BE1-034 | Authentication Middleware | Validate JWT tokens on protected routes. | High | Pending | BE1-039 | Swagger Documentation | Document authentication, user, institute, and branch APIs. | Medium | Pending
BE1-002 | Database Configuration | Configure MongoDB connection using Mongoose. | High | Pending | BE1-008 | Login API | Implement login using Email, Mobile Number, or Username. | High | Pending | BE1-016 | Permission Management | Implement module-level permission system. | High | Pending | BE1-021 | User Profile API | Retrieve authenticated user profile. | High | Pending | BE1-027 | Branch CRUD APIs | Develop APIs to manage institute branches. | High | Pending | BE1-032 | Document Upload | Upload user documents with validation. | Medium | Pending | BE1-035 | Rate Limiting | Prevent brute-force login attacks. | High | Pending | BE1-040 | API Testing | Write unit and integration tests using Jest and Supertest. | Medium | Pending
BE1-003 | Environment Configuration | Configure environment variables for development and production. | High | Pending | BE1-009 | JWT Authentication | Generate and validate Access Tokens and Refresh Tokens. | High | Pending | BE1-017 | Authorization Middleware | Restrict API access based on user roles and permissions. | High | Pending | BE1-022 | Update Profile API | Update user information and profile image. | High | Pending | BE1-028 | Academic Year API | Manage academic years and sessions. | Medium | Pending | BE1-033 | File Validation | Validate file type and file size before upload. | Medium | Pending | BE1-036 | Security Headers | Configure Helmet, CORS, and security middleware. | High | Pending | BE1-041 | Postman Collection | Create Postman collection for all implemented APIs. | High | Pending
BE1-004 | Global Error Handler | Implement centralized error handling middleware. | High | Pending | BE1-010 | Forgot Password API | Send OTP via Email for password recovery. | High | Pending | BE1-018 | Super Admin Access | Configure unrestricted access for Super Administrator. | High | Pending | BE1-023 | User Status API | Activate, Suspend, Lock, Unlock, and Archive user accounts. | High | Pending | BE1-029 | Holiday Calendar API | Create APIs for institute holidays and working days. | Medium | Pending | [5 empty] | BE1-037 | Password Encryption | Encrypt passwords using BCrypt. | High | Pending
BE1-005 | Request Validation | Create reusable validation middleware using Express Validator/Zod. | High | Pending | BE1-011 | Verify OTP API | Validate OTP before allowing password reset. | High | Pending | BE1-019 | Branch-Level Access | Restrict data access according to assigned branches. | Medium | Pending | BE1-024 | User Search API | Support filtering by role, department, branch, and status. | Medium | Pending | BE1-030 | Institute Settings API | Store branding, notifications, and operational settings. | Medium | Pending | [5 empty] | BE1-038 | Input Sanitization | Protect against NoSQL Injection and XSS attacks. | High | Pending
BE1-006 | Logging System | Configure request, error, and activity logging using Winston/Morgan. | Medium | Pending | BE1-012 | Reset Password API | Securely reset password after OTP verification. | High | Pending | [5 empty] | BE1-025 | Login History API | Maintain user login history. | Medium | Pending
[5 empty] | BE1-013 | Logout API | Invalidate refresh tokens and terminate sessions. | High | Pending
[5 empty] | BE1-014 | Session Management | Implement secure session tracking and expiration. | Medium | Pending
Database Architecture
Database: cims_db
1. Users Collection
Collection Name
users
Field | Type | Required | Description
_id | ObjectId | Yes | Primary Key
employeeId | String | Yes | Unique User ID
firstName | String | Yes | First Name
lastName | String | Yes | Last Name
email | String | Yes | Unique Email
mobile | String | Yes | Mobile Number
password | String | Yes | Encrypted Password
profileImage | String | No | Cloudinary URL
roleId | ObjectId | Yes | Reference to Roles
instituteId | ObjectId | Yes | Institute Reference
branchId | ObjectId | Yes | Branch Reference
department | String | No | Department
designation | String | No | Job Title
status | String | Yes | Active / Suspended / Inactive
lastLogin | Date | No | Last Login Time
createdBy | ObjectId | No | User Reference
updatedBy | ObjectId | No | User Reference
createdAt | Date | Yes | Timestamp
updatedAt | Date | Yes | Timestamp
2. Roles Collection
Collection Name
roles
Field | Type | Description
_id | ObjectId | Primary Key
roleName | String | Admin / Faculty / Student / Parent
description | String | Role Description
permissions | Array<ObjectId> | Permission References
createdAt | Date | Timestamp
updatedAt | Date | Timestamp
3. Permissions Collection
Collection Name
permissions
Field | Type | Description
_id | ObjectId | Primary Key
module | String | Student Module
action | String | Create
description | String | Permission Description
createdAt | Date | Timestamp
Example
Student
Create
Read
Update
Delete
Attendance
Mark
Update
Fee
Collect
Refund
4. User Sessions Collection
Collection Name
sessions
Field | Type | Description
_id | ObjectId | Primary Key
userId | ObjectId | User Reference
refreshToken | String | JWT Refresh Token
device | String | Device Name
browser | String | Browser
ipAddress | String | IP Address
loginTime | Date | Login Time
logoutTime | Date | Logout Time
status | String | Active / Expired
5. OTP Collection
Collection Name
otp_verifications
Field | Type
_id | ObjectId
userId | ObjectId
email | String
otp | String
expiresAt | Date
verified | Boolean
createdAt | Date
6. Institute Collection
Collection Name
institutes
Field | Type
_id | ObjectId
instituteName | String
instituteCode | String
logo | String
email | String
phone | String
website | String
address | String
city | String
state | String
country | String
postalCode | String
establishedYear | Number
principalName | String
status | String
createdAt | Date
updatedAt | Date
7. Branch Collection
Collection Name
branches
Field | Type
_id | ObjectId
instituteId | ObjectId
branchCode | String
branchName | String
address | String
city | String
state | String
phone | String
email | String
managerId | ObjectId
status | String
createdAt | Date
updatedAt | Date
8. Academic Years Collection
Collection Name
academic_years
Field | Type
_id | ObjectId
yearName | String
startDate | Date
endDate | Date
currentYear | Boolean
status | String
9. Holidays Collection
Collection Name
holidays
Field | Type
_id | ObjectId
holidayName | String
holidayDate | Date
description | String
branchId | ObjectId
createdAt | Date
10. System Settings Collection
Collection Name
system_settings
Field | Type
_id | ObjectId
instituteId | ObjectId
logo | String
primaryColor | String
secondaryColor | String
timezone | String
currency | String
language | String
attendanceMethod | String
feeSettings | Object
notificationSettings | Object
backupSettings | Object
updatedAt | Date
11. Login History Collection
Collection Name
login_history
Field | Type
_id | ObjectId
userId | ObjectId
loginTime | Date
logoutTime | Date
ipAddress | String
browser | String
operatingSystem | String
location | String
status | String
Entity Relationship Diagram (ERD)
Institute
│
├──────────────┐
│ │
Branches System Settings
│
│
Users
│
├──────── Role
│ │
│ │
│ Permissions
│
├──────── Login History
│
├──────── User Sessions
│
└──────── OTP Verification
Institute
│
Academic Year
Branch
│
Holiday

## M2 Malin
Team Member 2 – Frontend Task Assignment
Role: Frontend Developer (Student, Parent, Course & Batch Management)
Technology Stack |  |  |  | Malin
· React.js
· TypeScript
· Tailwind CSS
· React Router
· Axios
· React Hook Form
· React Query
· Context API
Sprint 1 - Student Management |  |  |  |  | Sprint 2 - Parent Portal |  |  |  |  | Sprint 3 - Course Management |  |  |  |  | Sprint 4 - Batch Management |  |  |  |  | Sprint 5 - Shared Components |  |  |  |  | Sprint 6 - API Integration
Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status
FE2-001 | Student Dashboard | Design dashboard displaying total students, active students, new admissions, and student statistics. | High | Pending | FE2-011 | Parent Login | Create secure parent login page. | High | Pending | FE2-021 | Course List | Display all available courses in a responsive table. | High | Pending | FE2-027 | Batch List | Display all batches with search and filters. | High | Pending | FE2-033 | Student Card | Create reusable student information card. | High | Pending | FE2-041 | Student APIs | Integrate CRUD operations for student management. | High | Pending
FE2-002 | Student List | Create searchable and paginated student table with filters. | High | Pending | FE2-012 | Parent Dashboard | Display attendance, fees, exams, homework, and announcements. | High | Pending | FE2-022 | Add Course | Create form for adding new courses with validation. | High | Pending | FE2-028 | Add Batch | Create batch creation form with faculty and classroom selection. | High | Pending | FE2-034 | Parent Card | Design reusable parent profile card. | Medium | Pending | FE2-042 | Parent APIs | Connect parent dashboard and profile APIs. | High | Pending
FE2-003 | Student Registration | Develop multi-step admission form with personal, academic, parent, and document details. | High | Pending | FE2-013 | Child Profile | Show complete student information for linked child. | High | Pending | FE2-023 | Edit Course | Allow administrators to update course details. | High | Pending | FE2-029 | Edit Batch | Update batch details and schedules. | High | Pending | FE2-035 | Course Card | Create reusable course display card. | Medium | Pending | FE2-043 | Course APIs | Integrate course management APIs. | High | Pending
FE2-004 | Student Profile | Design detailed student profile with personal, academic, attendance, fee, and examination information. | High | Pending | FE2-014 | Attendance View | Display daily, weekly, and monthly attendance reports. | High | Pending | FE2-024 | Course Details | Display syllabus, duration, fee structure, faculty, and batches. | High | Pending | FE2-030 | Batch Details | Display enrolled students, faculty, timetable, and attendance. | High | Pending | FE2-036 | Batch Card | Develop batch summary card. | Medium | Pending | FE2-044 | Batch APIs | Connect batch management APIs. | High | Pending
FE2-005 | Edit Student | Create edit student profile page with validation. | High | Pending | FE2-015 | Fee Details | Show payment history, due amounts, and downloadable receipts. | High | Pending | FE2-025 | Course Search | Implement search and filtering options. | Medium | Pending | FE2-031 | Student Allocation | Assign and remove students from batches. | High | Pending | FE2-037 | Search Component | Build reusable search bar with filters. | High | Pending | FE2-045 | File Upload API | Integrate document upload service. | Medium | Pending
FE2-006 | Student Status | Implement Active, Inactive, Alumni, Completed, and Suspended status management. | Medium | Pending | FE2-016 | Exam Results | Display marks, grades, rankings, and report cards. | High | Pending | FE2-026 | Course Dashboard | Show enrollment statistics and revenue summary. | Medium | Pending | FE2-032 | Batch Analytics | Show attendance, performance, and fee collection statistics. | Medium | Pending | FE2-038 | Data Table | Create reusable table with sorting, pagination, and filtering. | High | Pending
FE2-007 | Student Search | Add advanced search and filtering by course, batch, branch, fee status, and attendance. | High | Pending | FE2-017 | Homework & Assignments | Display assignments, homework, deadlines, and submission status. | Medium | Pending | [10 empty] | FE2-039 | File Upload | Develop drag-and-drop document upload component. | Medium | Pending
FE2-008 | Student Documents | Create document upload and preview interface. | Medium | Pending | FE2-018 | Notifications | Display institute announcements and alerts. | Medium | Pending | [10 empty] | FE2-040 | Profile Tabs | Build reusable tab navigation for profile sections. | Medium | Pending
FE2-009 | Student Transfer | Develop batch transfer and branch transfer UI. | Medium | Pending | FE2-019 | Download Reports | Enable PDF download for attendance, fee receipts, and report cards. | Medium | Pending
FE2-010 | Student Activity Timeline | Display complete student activity history. | Low | Pending | FE2-020 | Multiple Child Support | Allow parents to switch between multiple children. | Medium | Pending
Backend Task Assignment Role: Backend Developer (Student, Parent, Course & Batch Management) Technology Stack Node.js Express.js TypeScript MongoDB (Mongoose) JWT Authentication (Provided by Team Member 1) Multer Cloudinary Express Validator Jest Swagger
Sprint 1 - Student Management |  |  |  |  | Sprint 2 - Parent Management |  |  |  |  | Sprint 3 - Course Management |  |  |  |  | Sprint 4 - Batch Management |  |  |  |  | Sprint 5 - File Upload & Document Management |  |  |  |  | Sprint 6 - Validation & Business Rules |  |  |  |  | Sprint 7 - API Documentation & Testing
Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status
BE2-001 | Student Schema | Design Student database schema with all required fields. | High | Pending | BE2-009 | Parent Schema | Design Parent database schema. | High | Pending | BE2-015 | Course Schema | Design Course database schema. | High | Pending | BE2-021 | Batch Schema | Design Batch database schema. | High | Pending | BE2-028 | Student Document Upload | Upload Aadhaar, certificates, photos, and supporting documents. | High | Pending | BE2-031 | Admission Validation | Prevent duplicate admission numbers and invalid enrollments. | High | Pending | BE2-035 | Swagger Documentation | Document Student, Parent, Course, and Batch APIs. | Medium | Pending
BE2-002 | Student CRUD APIs | Develop Create, Read, Update, Delete APIs for students. | High | Pending | BE2-010 | Parent CRUD APIs | Create APIs to manage parent records. | High | Pending | BE2-016 | Course CRUD APIs | Implement complete course management APIs. | High | Pending | BE2-022 | Batch CRUD APIs | Develop batch management APIs. | High | Pending | BE2-029 | Document Validation | Validate file format and size before upload. | Medium | Pending | BE2-032 | Course Eligibility Validation | Validate age and prerequisite requirements. | Medium | Pending | BE2-036 | Unit Testing | Write Jest test cases for service and controller layers. | Medium | Pending
BE2-003 | Student Admission API | Implement student admission workflow with automatic Student ID generation. | High | Pending | BE2-011 | Parent-Student Linking API | Link one or more students with parent accounts. | High | Pending | BE2-017 | Subject Management API | Manage subjects/modules within each course. | High | Pending | BE2-023 | Student Allocation API | Assign students to batches. | High | Pending | BE2-030 | Cloud Storage Integration | Store documents securely using Cloudinary or AWS S3. | Medium | Pending | BE2-033 | Student Data Validation | Validate email, mobile number, and mandatory fields. | High | Pending | BE2-037 | Integration Testing | Test complete workflows including admission and enrollment. | Medium | Pending
BE2-004 | Student Profile API | Retrieve complete student profile including academic and personal details. | High | Pending | BE2-012 | Parent Dashboard API | Return attendance, fees, results, homework, and announcements for linked students. | High | Pending | BE2-018 | Course Enrollment API | Enroll students into selected courses. | High | Pending | BE2-024 | Faculty Allocation API | Assign faculty to batches. | High | Pending | [5 empty] | BE2-034 | Batch Capacity Validation | Prevent enrollment when batch capacity is exceeded. | High | Pending | BE2-038 | Postman Collection | Prepare API collection for all implemented endpoints. | High | Pending
BE2-005 | Student Search API | Implement advanced search with filters (course, batch, branch, fee status). | High | Pending | BE2-013 | Parent Notification API | Retrieve notifications related to their children. | Medium | Pending | BE2-019 | Course Search API | Search and filter courses. | Medium | Pending | BE2-025 | Batch Transfer API | Transfer students between batches while maintaining history. | Medium | Pending
BE2-006 | Student Status API | Manage Active, Inactive, Suspended, Completed, and Alumni statuses. | Medium | Pending | BE2-014 | Parent Report API | Generate attendance and academic reports for parents. | Medium | Pending | BE2-020 | Course Statistics API | Return enrollment count, revenue, and completion statistics. | Medium | Pending | BE2-026 | Batch Capacity Validation | Validate batch capacity before admission. | High | Pending
BE2-007 | Student Transfer API | Support student transfer between branches and batches while preserving history. | Medium | Pending | [10 empty] | BE2-027 | Batch Analytics API | Return attendance, fee collection, and student statistics. | Medium | Pending
BE2-008 | Student History API | Maintain complete academic and admission history. | Medium | Pen
Database Architecture
Module Ownership
· Student Management
· Parent Management
· Course Management
· Subject Management
· Batch Management
· Student Enrollment
· Student Documents
1. Students Collection
Collection Name
students
Field | Type | Required | Description
_id | ObjectId | Yes | Primary Key
studentId | String | Yes | Unique Student ID
admissionNumber | String | Yes | Admission Number
firstName | String | Yes | Student First Name
lastName | String | Yes | Student Last Name
gender | String | Yes | Male/Female/Other
dateOfBirth | Date | Yes | DOB
email | String | No | Email Address
mobile | String | Yes | Mobile Number
address | Object | Yes | Full Address
bloodGroup | String | No | Blood Group
photo | String | No | Profile Image URL
instituteId | ObjectId | Yes | Reference Institutes
branchId | ObjectId | Yes | Reference Branches
courseId | ObjectId | Yes | Reference Courses
batchId | ObjectId | Yes | Reference Batches
parentId | ObjectId | Yes | Reference Parents
admissionDate | Date | Yes | Admission Date
status | String | Yes | Active/Inactive/Completed
createdAt | Date | Yes | Timestamp
updatedAt | Date | Yes | Timestamp
2. Parents Collection
Collection Name
parents
Field | Type
_id | ObjectId
parentId | String
fatherName | String
motherName | String
guardianName | String
relation | String
mobile | String
alternateMobile | String
email | String
occupation | String
annualIncome | Number
address | Object
userId | ObjectId
createdAt | Date
updatedAt | Date
3. Courses Collection
Collection Name
courses
Field | Type
_id | ObjectId
courseCode | String
courseName | String
description | String
duration | Number
durationType | String
feeStructure | Number
eligibility | String
totalSubjects | Number
status | String
createdAt | Date
updatedAt | Date
4. Subjects Collection
Collection Name
subjects
Field | Type
_id | ObjectId
subjectCode | String
subjectName | String
courseId | ObjectId
description | String
credits | Number
totalHours | Number
createdAt | Date
updatedAt | Date
5. Batches Collection
Collection Name
batches
Field | Type
_id | ObjectId
batchCode | String
batchName | String
courseId | ObjectId
facultyId | ObjectId
classroom | String
capacity | Number
currentStrength | Number
startDate | Date
endDate | Date
status | String
createdAt | Date
updatedAt | Date
6. Student Enrollment Collection
Collection Name
enrollments
Field | Type
_id | ObjectId
studentId | ObjectId
batchId | ObjectId
courseId | ObjectId
enrollmentDate | Date
enrollmentStatus | String
remarks | String
createdAt | Date
7. Student Documents Collection
Collection Name
student_documents
Field | Type
_id | ObjectId
studentId | ObjectId
documentType | String
fileName | String
fileUrl | String
uploadedBy | ObjectId
uploadedAt | Date
8. Student Transfer History Collection
Collection Name
student_transfer_history
Field | Type
_id | ObjectId
studentId | ObjectId
oldBatchId | ObjectId
newBatchId | ObjectId
oldCourseId | ObjectId
newCourseId | ObjectId
oldBranchId | ObjectId
newBranchId | ObjectId
transferReason | String
transferDate | Date
approvedBy | ObjectId
9. Admission Applications Collection
Collection Name
admission_applications
Field | Type
_id | ObjectId
applicationNumber | String
studentName | String
parentName | String
mobile | String
courseApplied | ObjectId
status | String
applicationDate | Date
approvedBy | ObjectId
10. Student Activity Logs Collection
Collection Name
student_activity_logs
Field | Type
_id | ObjectId
studentId | ObjectId
activityType | String
description | String
performedBy | ObjectId
createdAt | Date
Entity Relationship Diagram (ERD)
Institute
│
Branch
│
Course
│
├──────── Subjects
│
└──────── Batches
│
Faculty (Team 3)
│
Enrollments
│
Students
│
├──────── Parents
├──────── Student Documents
├──────── Transfer History
└──────── Activity Logs
Admission Applications
│
▼
Students

## M3 Nanda
Team Member 3 – Frontend Task Assignment
Role: Frontend Developer (Faculty, Attendance, Timetable & Academic Management)
Technology Stack
· React.js |  |  |  | Nanda
· TypeScript
· Tailwind CSS
· React Router
· Axios
· React Hook Form
· React Query
· FullCalendar (for timetable)
· Chart.js / Recharts
Sprint 1 - Faculty Management |  |  |  |  | Sprint 2 - Timetable Management |  |  |  |  | Sprint 3 - Attendance Management |  |  |  |  | Sprint 4 - Assignment & Homework Management |  |  |  |  | Sprint 5 - Study Material Management |  |  |  |  | Sprint 6 - Shared Components |  |  |  |  | Sprint 7 - API Integration
Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status
FE3-001 | Faculty Dashboard | Design dashboard showing faculty count, assigned batches, attendance, and schedules. | High | Pending | FE3-009 | Timetable Dashboard | Display daily, weekly, and monthly schedules. | High | Pending | FE3-017 | Attendance Dashboard | Show attendance overview and statistics. | High | Pending | FE3-026 | Assignment List | Display all assignments with filtering options. | High | Pending | FE3-033 | Study Material Dashboard | Display uploaded learning resources. | Medium | Pending | FE3-040 | Faculty Card | Create reusable faculty profile card. | Medium | Pending | FE3-045 | Faculty APIs | Integrate CRUD operations for faculty management. | High | Pending
FE3-002 | Faculty List | Create searchable and paginated faculty table. | High | Pending | FE3-010 | Create Timetable | Develop timetable creation form with course, faculty, classroom, and batch selection. | High | Pending | FE3-018 | Manual Attendance | Develop attendance marking interface with Present, Absent, Late, Half-Day, and Leave options. | High | Pending | FE3-027 | Create Assignment | Develop assignment creation form with attachments and deadlines. | High | Pending | FE3-034 | Upload Study Material | Create upload interface for PDF, PPT, Video, Images, and Notes. | High | Pending | FE3-041 | Attendance Table | Build reusable attendance table with filters and pagination. | High | Pending | FE3-046 | Timetable APIs | Connect timetable creation and update APIs. | High | Pending
FE3-003 | Add Faculty | Develop faculty registration form with personal, qualification, and department details. | High | Pending | FE3-011 | Timetable Calendar | Implement interactive calendar view for schedules. | High | Pending | FE3-019 | Face Recognition UI | Design interface for AI-based face attendance. | High | Pending | FE3-028 | Assignment Details | Show assignment description, files, due dates, and submissions. | High | Pending | FE3-035 | Material Categories | Organize materials by course, subject, chapter, and batch. | High | Pending | FE3-042 | Calendar Component | Develop reusable calendar for timetable management. | High | Pending | FE3-047 | Attendance APIs | Integrate manual, face recognition, and biometric attendance APIs. | High | Pending
FE3-004 | Faculty Profile | Display faculty profile including assigned courses, batches, and timetable. | High | Pending | FE3-012 | Edit Timetable | Update existing schedules. | High | Pending | FE3-020 | Fingerprint Attendance UI | Create biometric attendance verification screen. | High | Pending | FE3-029 | Homework Management | Create homework creation and tracking interface. | Medium | Pending | FE3-036 | Material Library | Display searchable repository of study materials. | High | Pending | FE3-043 | File Upload Component | Build drag-and-drop upload component for assignments and study materials. | High | Pending | FE3-048 | Assignment APIs | Connect assignment and homework management APIs. | High | Pending
FE3-005 | Edit Faculty | Create faculty update page with validation. | High | Pending | FE3-013 | Conflict Alerts | Display faculty and classroom scheduling conflicts. | High | Pending | FE3-021 | QR Attendance UI | Design QR code attendance page (future-ready). | Medium | Pending | FE3-030 | Student Submission View | Display submitted assignments and submission status. | High | Pending | FE3-037 | Material Preview | Enable preview for PDF, images, and videos. | Medium | Pending | FE3-044 | Analytics Charts | Create reusable attendance and academic performance charts. | Medium | Pending | FE3-049 | Study Material APIs | Integrate upload, download, and management APIs. | High | Pending
FE3-006 | Faculty Assignment | Assign faculty to courses, subjects, and batches. | High | Pending | FE3-014 | Holiday View | Show holidays and special events in the timetable. | Medium | Pending | FE3-022 | Attendance History | Display attendance history with filters. | High | Pending | FE3-031 | Evaluation Interface | Faculty marks assignments and provides feedback. | High | Pending | FE3-038 | Material Version History | Show updated versions of learning materials. | Low | Pending
FE3-007 | Faculty Transfer | Create faculty transfer UI between branches. | Medium | Pending | FE3-015 | Student Timetable | Display personalized timetable for students. | Medium | Pending | FE3-023 | Attendance Reports | Generate daily, weekly, monthly, and yearly attendance views. | High | Pending | FE3-032 | Assignment Reminders | Display upcoming deadlines and reminders. | Medium | Pending | FE3-039 | Download Center | Allow students to download authorized study materials. | Medium | Pending
FE3-008 | Faculty Search | Add filters by department, branch, and status. | Medium | Pending | FE3-016 | Faculty Timetable | Display personalized timetable for faculty members. | Medium | Pending | FE3-024 | Attendance Analytics | Show attendance percentage and trends using charts. | Medium | Pending
[10 empty] | FE3-025 | Attendance Correction | Create attendance correction request and approval interface. | Medium | Pending
Backend Task Assignment Role: Backend Developer (Faculty, Attendance & Academic Management) Technology Stack Node.js Express.js TypeScript MongoDB (Mongoose) JWT Authentication Multer Cloudinary / AWS S3 Face Recognition API (Future) Fingerprint SDK Integration (Future) Jest Swagger
Sprint 1 - Faculty Management |  |  |  |  | Sprint 2 - Timetable Management |  |  |  |  | Sprint 3 - Attendance Management |  |  |  |  | Sprint 4 - Assignment & Homework Management |  |  |  |  | Sprint 5 - Study Material Management |  |  |  |  | Sprint 6 - File Upload & Storage |  |  |  |  | Sprint 7 - API Documentation & Testing
Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status
BE3-001 | Faculty Schema | Design Faculty database schema. | High | Pending | BE3-007 | Timetable Schema | Design timetable database schema. | High | Pending | BE3-013 | Attendance Schema | Design attendance database schema. | High | Pending | BE3-021 | Assignment Schema | Design assignment database schema. | High | Pending | BE3-027 | Study Material Schema | Design study material database schema. | High | Pending | BE3-033 | File Upload Service | Configure secure file upload service using Multer. | High | Pending | BE3-036 | Swagger Documentation | Document Faculty, Timetable, Attendance, Assignment, and Study Material APIs. | Medium | Pending
BE3-002 | Faculty CRUD APIs | Develop Create, Read, Update, Delete APIs for faculty. | High | Pending | BE3-008 | Timetable CRUD APIs | Develop APIs for timetable creation and management. | High | Pending | BE3-014 | Manual Attendance API | Record attendance manually for classes. | High | Pending | BE3-022 | Assignment CRUD APIs | Develop APIs for creating, updating, and deleting assignments. | High | Pending | BE3-028 | Upload Study Material API | Upload PDFs, videos, notes, PPTs, and images. | High | Pending | BE3-034 | Cloud Storage | Store files using Cloudinary or AWS S3. | High | Pending | BE3-037 | Unit Testing | Write Jest test cases for services and controllers. | Medium | Pending
BE3-003 | Faculty Profile API | Retrieve faculty profile with assigned courses and batches. | High | Pending | BE3-009 | Conflict Detection API | Validate classroom and faculty scheduling conflicts. | High | Pending | BE3-015 | Face Recognition API | Integrate AI face recognition attendance endpoint. | High | Pending | BE3-023 | Homework CRUD APIs | Develop homework management APIs. | High | Pending | BE3-029 | Material Download API | Allow authorized users to download study materials. | High | Pending | BE3-035 | File Validation | Validate file size, format, and permissions. | Medium | Pending | BE3-038 | Integration Testing | Test attendance, timetable, and assignment workflows. | Medium | Pending
BE3-004 | Faculty Assignment API | Assign faculty to courses, subjects, and batches. | High | Pending | BE3-010 | Student Timetable API | Return personalized timetable for students. | High | Pending | BE3-016 | Fingerprint Attendance API | Integrate biometric attendance endpoint. | High | Pending | BE3-024 | Student Submission API | Accept assignment submissions from students. | High | Pending | BE3-030 | Material Category API | Organize materials by course, subject, chapter, and batch. | High | Pending | [5 empty] | BE3-039 | Postman Collection | Prepare Postman collection for all APIs. | High | Pending
BE3-005 | Faculty Transfer API | Transfer faculty between branches while preserving history. | Medium | Pending | BE3-011 | Faculty Timetable API | Return personalized timetable for faculty. | High | Pending | BE3-017 | QR Attendance API | Develop QR-based attendance API (future-ready). | Medium | Pending | BE3-025 | Assignment Evaluation API | Faculty can evaluate assignments and provide feedback. | High | Pending | BE3-031 | Material Version API | Maintain version history for updated materials. | Medium | Pending
BE3-006 | Faculty Search API | Search faculty by department, branch, and specialization. | Medium | Pending | BE3-012 | Holiday Integration API | Exclude holidays while generating schedules. | Medium | Pending | BE3-018 | Attendance Correction API | Support attendance correction requests and approvals. | Medium | Pending | BE3-026 | Assignment Reminder API | Send reminders before assignment deadlines. | Medium | Pending | BE3-032 | Material Search API | Search study materials by keyword and category. | Medium | Pending
[10 empty] | BE3-019 | Attendance History API | Retrieve daily, weekly, monthly, and yearly attendance records. | High | Pending
[10 empty] | BE3-020 | Attendance Analytics API | Calculate attendance percentages and trends. | High | Pending | [5 empty] | Step-by-Step Execution Process
[20 empty] | Backend |  |  |  |  | cd backend
[20 empty] | # 1. Environment setup |  |  |  |  | npm install
Database Architecture | [9 empty] | Real Pages (16) | [9 empty] | cd backend |  |  |  |  | npx prisma db push # creates tables in Supabase
Module Ownership | [9 empty] | # | Route | Page File | [7 empty] | copy .env.example .env # fill in DB credentials, JWT secrets |  |  |  |  | npm run seed # full seed (50 faculty, 100 students, etc.)
· Faculty Management | [9 empty] | 1 | / | src/pages/Dashboard.tsx | [12 empty] | npm run seed:users # add 4 specific users
· Attendance Management | [9 empty] | 2 | /faculty | src/features/faculty/pages/FacultyListPage.tsx | [7 empty] | # 2. Install & build |  |  |  |  | npm run seed:continue # attendance, transfers, homework
· Timetable Management | [9 empty] | 3 | /faculty/add | src/features/add-faculty/pages/AddFacultyPage.tsx | [7 empty] | npm install |  |  |  |  | npm run dev # starts on :5000
· Assignment Management | [9 empty] | 4 | /faculty/edit/:id | src/features/add-faculty/pages/EditFacultyPage.tsx | [7 empty] | npx prisma generate # generate Prisma client from schema
· Homework Management | [9 empty] | 5 | /faculty/profile/:id | src/features/faculty-profile/pages/FacultyProfilePage.tsx | [7 empty] | npx prisma db push # sync schema to PostgreSQL (use `npx prisma migrate dev` for migrations) |  |  |  |  | # Frontend (separate terminal)
· Study Material Management | [9 empty] | 6 | /faculty/assign | src/features/faculty-assignment/pages/FacultyAssignmentPage.tsx | [7 empty] | npx tsc --noEmit # verify TypeScript (should pass) |  |  |  |  | cd ..
1. Faculty Collection | [9 empty] | 7 | /faculty/transfer | src/features/faculty-transfer/pages/FacultyTransferPage.tsx | [12 empty] | npm install
Collection Name | [9 empty] | 8 | /faculty/search | src/features/faculty-search/pages/FacultySearchPage.tsx | [7 empty] | # 3. Seed data (if seed script exists) |  |  |  |  | npm run dev
faculties | [9 empty] | 9 | /schedule | src/features/timetable/pages/TimetableDashboard.tsx | [7 empty] | npx prisma db seed
Field | Type | Required | Description | [6 empty] | 10 | /timetable | alias — same as /schedule
_id | ObjectId | Yes | Primary Key | [6 empty] | 11 | /timetable/create | src/features/create-timetable/pages/CreateTimetablePage.tsx | [7 empty] | # 4. Start server
facultyId | String | Yes | Unique Faculty ID | [6 empty] | 12 | /timetable/edit/:id | src/features/create-timetable/pages/EditTimetablePage.tsx | [7 empty] | npm run dev # starts on http://localhost:5000
employeeId | String | Yes | Employee Code | [6 empty] | 13 | /timetable/calendar | src/features/interactive-calendar/pages/InteractiveCalendarPage.tsx
firstName | String | Yes | Faculty First Name | [6 empty] | 14 | /holidays | src/features/holiday-management/pages/HolidayManagementPage.tsx | [7 empty] | # 5. Verify health
lastName | String | Yes | Faculty Last Name | [6 empty] | 15 | /student/timetable | src/features/student-timetable/pages/StudentTimetablePage.tsx | [7 empty] | curl http://localhost:5000/api/health
email | String | Yes | Email Address | [6 empty] | 16 | /faculty/timetable | src/features/faculty-timetable/pages/FacultyTimetablePage.tsx | [7 empty] | # → { "success": true, "message": "College ERP API is running", ... }
mobile | String | Yes | Mobile Number | [6 empty] | Placeholder Pages (3 — all reuse Dashboard.tsx)
qualification | String | Yes | Highest Qualification | [6 empty] | # | Route | Note | [7 empty] | # 6. Swagger docs
specialization | String | Yes | Subject Specialization | [6 empty] | 1 | /departments | Renders main Dashboard | [7 empty] | # → http://localhost:5000/api-docs
experience | Number | No | Experience (Years) | [6 empty] | 2 | /courses | Renders main Dashboard | [7 empty] | Frontend
joiningDate | Date | Yes | Joining Date | [6 empty] | 3 | /assignments | Renders main Dashboard | [7 empty] | # 1. Environment setup
userId | ObjectId | Yes | Reference Users Collection | [16 empty] | cd .. # back to project root
instituteId | ObjectId | Yes | Reference Institutes | [16 empty] | # .env already created with VITE_API_BASE_URL=http://localhost:5000/api
branchId | ObjectId | Yes | Reference Branches
status | String | Yes | Active / Inactive | [16 empty] | # 2. Install & run
createdAt | Date | Yes | Timestamp | [16 empty] | npm install
updatedAt | Date | Yes | Timestamp | [16 empty] | npx tsc --noEmit # verify TypeScript (should pass — 0 errors)
2. Faculty Assignments Collection
Collection Name | [19 empty] | # 3. Start dev server
faculty_assignments | [19 empty] | npm run dev # starts on http://localhost:5173
Field | Type | [18 empty] | Verification Workflow
_id | ObjectId | [18 empty] | Once both servers are running, test the connected pages:
facultyId | ObjectId | [18 empty] | Test | Page URL | Expected Behavior
courseId | ObjectId | [18 empty] | Faculty List | /faculty | Renders faculty list from GET /api/faculty
subjectId | ObjectId | [18 empty] | Dashboard | /dashboard | Shows stats from attendance/timetable/faculty APIs
batchId | ObjectId | [18 empty] | Manual Attendance | /attendance/manual | Student dropdown populated from GET /api/student
academicYearId | ObjectId | [18 empty] | Face Recognition | /attendance/face | Captures face → calls POST /api/attendance/face/mark
assignedDate | Date | [18 empty] | Fingerprint | /attendance/fingerprint | Scans fingerprint → calls POST /api/attendance/fingerprint/mark
assignedBy | ObjectId | [18 empty] | QR Attendance | /attendance/qr | Generates QR via POST /api/attendance/qr/generate
status | String | [18 empty] | Evaluation | /evaluation | Loads submissions from GET /api/submissions
3. Timetable Collection | [19 empty] | Faculty Assignments | /faculty/assignments | Select faculty → loads assignments from API
Collection Name | [19 empty] | Faculty Transfer | /faculty/transfer | Select faculty → loads transfer history from API
timetables | [19 empty] | Download Center | /downloads | Downloads materials from GET /api/materials
Field | Type | [18 empty] | File Upload | any upload component | Uploads via POST /api/uplo
_id | ObjectId
batchId | ObjectId
courseId | ObjectId
subjectId | ObjectId
facultyId | ObjectId
classroom | String
dayOfWeek | String
startTime | String
endTime | String
semester | String
academicYearId | ObjectId
status | String
createdAt | Date
4. Attendance Collection
Collection Name
attendance
Field | Type
_id | ObjectId
studentId | ObjectId
facultyId | ObjectId
batchId | ObjectId
subjectId | ObjectId
attendanceDate | Date
attendanceType | String (Manual / Face / Fingerprint / QR)
status | String (Present / Absent / Late / Leave)
remarks | String
markedBy | ObjectId
createdAt | Date
5. Attendance Correction Collection
Collection Name
attendance_corrections
Field | Type
_id | ObjectId
attendanceId | ObjectId
requestedBy | ObjectId
approvedBy | ObjectId
oldStatus | String
newStatus | String
reason | String
requestDate | Date
approvalDate | Date
status | String
6. Assignments Collection
Collection Name
assignments
Field | Type
_id | ObjectId
assignmentTitle | String
description | String
courseId | ObjectId
batchId | ObjectId
subjectId | ObjectId
facultyId | ObjectId
dueDate | Date
attachmentUrl | String
totalMarks | Number
createdAt | Date
7. Assignment Submissions Collection
Collection Name
assignment_submissions
Field | Type
_id | ObjectId
assignmentId | ObjectId
studentId | ObjectId
submissionUrl | String
submittedAt | Date
marksObtained | Number
feedback | String
evaluatedBy | ObjectId
evaluationDate | Date
8. Homework Collection
Collection Name
homeworks
Field | Type
_id | ObjectId
title | String
description | String
batchId | ObjectId
subjectId | ObjectId
facultyId | ObjectId
dueDate | Date
attachmentUrl | String
createdAt | Date
9. Study Materials Collection
Collection Name
study_materials
Field | Type
_id | ObjectId
title | String
description | String
courseId | ObjectId
batchId | ObjectId
subjectId | ObjectId
uploadedBy | ObjectId
materialType | String (PDF, PPT, Video, Image, Notes)
fileUrl | String
version | String
createdAt | Date
10. Attendance Analytics Collection
Collection Name
attendance_analytics
Field | Type
_id | ObjectId
studentId | ObjectId
batchId | ObjectId
month | Number
year | Number
totalClasses | Number
attendedClasses | Number
attendancePercentage | Number
updatedAt | Date
Entity Relationship Diagram (ERD)
Institutes
│
Branches
│
Faculties
│
Faculty Assignments
│
├──────────────┐
│ │
Courses Subjects
│ │
└─────── Timetables
│
Batches
│
┌────────┴────────┐
│ │
Attendance Assignments
│ │
Attendance Assignment
Corrections Submissions
│
Students
Faculties
│
Homework
│
Study Materials

## M4
Team Member 4 – Frontend Task Assignment
Role: Frontend Developer (Administration, Finance, Examination & Reports)
Technology Stack
· React.js
· TypeScript
· Tailwind CSS
· React Router
· Axios
· React Hook Form
· React Query
· Recharts / Chart.js
· React PDF Viewer (Optional)
Sprint 1 - Institute & Branch Management |  |  |  |  | Sprint 2 - User & Role Management |  |  |  |  | Sprint 3 - Fee Management |  |  |  |  | Sprint 4 - Examination Management |  |  |  |  | Sprint 5 - Reports & Certificates |  |  |  |  | Sprint 6 - Notifications & Analytics |  |  |  |  | Sprint 7 - Shared Components |  |  |  |  | Sprint 8 - API Integration
Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status
FE4-001 | Institute Dashboard | Design institute overview dashboard displaying branches, students, faculty, and revenue summary. | High | Pending | FE4-007 | User List | Create searchable and paginated user management table. | High | Pending | FE4-013 | Fee Dashboard | Display fee collection, pending dues, refunds, and revenue statistics. | High | Pending | FE4-020 | Examination Dashboard | Display upcoming exams, completed exams, and performance statistics. | High | Pending | FE4-026 | Reports Dashboard | Display all system reports with filters. | High | Pending | FE4-032 | Notification Center | Design centralized notification management interface. | High | Pending | FE4-038 | Chart Components | Build reusable bar, line, pie, and area chart components. | High | Pending | FE4-043 | Institute APIs | Integrate institute and branch management APIs. | High | Pending
FE4-002 | Institute Profile | Create institute profile page with logo, contact details, branding, and academic settings. | High | Pending | FE4-008 | Add User | Design user registration form with role assignment. | High | Pending | FE4-014 | Fee Structure | Create fee structure management interface for courses and batches. | High | Pending | FE4-021 | Create Examination | Develop examination creation form with subject, batch, schedule, and duration. | High | Pending | FE4-027 | Student Reports | Show admission, attendance, fee, and academic reports. | High | Pending | FE4-033 | Send Notifications | Create UI for sending SMS, Email, Push, and WhatsApp (future-ready) notifications. | Medium | Pending | FE4-039 | Report Table | Create reusable report table with filtering and pagination. | High | Pending | FE4-044 | User Management APIs | Connect user and role management APIs. | High | Pending
FE4-003 | Branch List | Display all branches with search and filtering options. | High | Pending | FE4-009 | Edit User | Allow administrators to update user information. | High | Pending | FE4-015 | Student Fee Details | Show fee invoices, payment history, outstanding balance, and receipts. | High | Pending | FE4-022 | Marks Entry | Design marks entry interface with validation. | High | Pending | FE4-028 | Financial Reports | Display revenue, fee collection, and outstanding reports. | High | Pending | FE4-034 | Announcement Management | Develop institute announcement creation and publishing interface. | Medium | Pending | FE4-040 | Invoice Card | Design reusable invoice and receipt component. | Medium | Pending | FE4-045 | Fee Management APIs | Integrate fee collection, invoices, and receipt APIs. | High | Pending
FE4-004 | Add Branch | Develop branch creation form with validation. | High | Pending | FE4-010 | Role Management | Create interface to assign and update user roles and permissions. | High | Pending | FE4-016 | Fee Collection | Design payment collection interface supporting multiple payment methods. | High | Pending | FE4-023 | Result Management | Display student results, grades, GPA, rankings, and report cards. | High | Pending | FE4-029 | Export Reports | Enable export to PDF, Excel, and CSV formats. | High | Pending | FE4-035 | Business Analytics Dashboard | Create interactive charts for admissions, attendance, fees, and examination performance. | High | Pending | FE4-041 | Export Buttons | Create reusable export buttons for PDF, Excel, and CSV. | Medium | Pending | FE4-046 | Examination APIs | Connect examination, marks, and result APIs. | High | Pending
FE4-005 | Edit Branch | Create interface for updating branch details. | High | Pending | FE4-011 | Permission Management | Design UI for configuring module-level permissions. | Medium | Pending | FE4-017 | Scholarship & Discount | Create scholarship and concession management page. | Medium | Pending | FE4-024 | Examination Analytics | Show subject-wise, batch-wise, and faculty-wise performance charts. | High | Pending | FE4-030 | Certificate Management | Display and generate completion, bonafide, and attendance certificates. | Medium | Pending | FE4-036 | Revenue Analytics | Display daily, monthly, quarterly, and yearly income charts. | High | Pending | FE4-042 | Statistics Cards | Develop reusable KPI cards for dashboards. | High | Pending | FE4-047 | Report APIs | Integrate report generation and export APIs. | High | Pending
FE4-006 | Branch Analytics | Display branch-wise admissions, attendance, fee collection, and examination statistics. | Medium | Pending | FE4-012 | Login History | Display login history and user activity logs. | Medium | Pending | FE4-018 | Refund Management | Design fee refund request and approval workflow. | Medium | Pending | FE4-025 | Revaluation Requests | Create revaluation request and approval interface. | Medium | Pending | FE4-031 | Certificate Preview | Create certificate preview and download page. | Medium | Pending | FE4-037 | Dashboard Widgets | Develop configurable dashboard widgets based on user roles. | Medium | Pending | [5 empty] | FE4-048 | Notification APIs | Connect notification and announcement APIs. | Medium | Pending
[10 empty] | FE4-019 | Receipt Generation | Display downloadable digital fee receipts. | Medium | Pending | [20 empty] | FE4-049 | Dashboard Analytics APIs | Integrate analytics and dashboard APIs. | High | Pending
Backend tasks assignment |  |  |  |  | Sprint 2 - Payment Gateway Integration |  |  |  |  | Sprint 3 - Examination Management |  |  |  |  | Sprint 4 - Reports & Analytics |  |  |  |  | Sprint 5 - Notifications & Communication |  |  |  |  | Sprint 6 - Audit Logs & System Settings |  |  |  |  | Sprint 7 - Dashboard & Analytics APIs |  |  |  |  | Sprint 8 - API Documentation & Testing
Sprint 1 - Fee Management |  |  |  |  | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status | Task ID | Task | Description | Priority | Status
Task ID | Task | Description | Priority | Status | BE4-009 | Razorpay Integration | Integrate Razorpay payment gateway. | High | Pending | BE4-014 | Examination Schema | Design examination database schema. | High | Pending | BE4-020 | Report Dashboard API | Generate dashboard statistics for administrators. | High | Pending | BE4-026 | Notification Schema | Design notification database schema. | High | Pending | BE4-032 | Audit Log Schema | Design audit log database schema. | High | Pending | BE4-037 | Dashboard Summary API | Return overall institute statistics. | High | Pending | BE4-042 | Swagger Documentation | Document all finance, examination, reporting, and notification APIs. | Medium | Pending
BE4-001 | Fee Structure Schema | Design fee structure schema for courses, batches, and installments. | High | Pending | BE4-010 | PhonePe Integration | Integrate PhonePe payment gateway. | Medium | Pending | BE4-015 | Examination CRUD APIs | Develop APIs for examination management. | High | Pending | BE4-021 | Student Report API | Generate admission, attendance, and academic reports. | High | Pending | BE4-027 | Email Notification API | Send emails for admissions, fee receipts, and results. | High | Pending | BE4-033 | Activity Logging API | Record user activities such as login, updates, and deletions. | High | Pending | BE4-038 | Revenue Analytics API | Generate revenue trends and financial insights. | High | Pending | BE4-043 | Unit Testing | Write Jest test cases for services and controllers. | Medium | Pending
BE4-002 | Fee CRUD APIs | Develop Create, Read, Update, Delete APIs for fee structures. | High | Pending | BE4-011 | Stripe Integration | Integrate Stripe payment gateway (optional). | Low | Pending | BE4-016 | Marks Entry API | Store subject-wise marks securely. | High | Pending | BE4-022 | Fee Report API | Generate fee collection, pending dues, and revenue reports. | High | Pending | BE4-028 | SMS Notification API | Send SMS alerts for fees, attendance, and announcements. | Medium | Pending | BE4-034 | Audit Report API | Retrieve audit logs with advanced filtering. | Medium | Pending | BE4-039 | Student Analytics API | Return admission and enrollment analytics. | High | Pending | BE4-044 | Integration Testing | Test complete payment, examination, and reporting workflows. | Medium | Pending
BE4-003 | Student Fee API | Manage student fee records and balances. | High | Pending | BE4-012 | Payment Verification API | Verify successful transactions and update payment status. | High | Pending | BE4-017 | Result Generation API | Automatically calculate grades, GPA, percentages, and rankings. | High | Pending | BE4-023 | Attendance Report API | Generate daily, monthly, and yearly attendance reports. | High | Pending | BE4-029 | Push Notification API | Develop push notification service for the mobile application. | Medium | Pending | BE4-035 | System Settings API | Manage institute configurations and preferences. | Medium | Pending | BE4-040 | Faculty Analytics API | Generate faculty workload and performance statistics. | Medium | Pending | BE4-045 | Postman Collection | Prepare Postman collection for all APIs. | High | Pending
BE4-004 | Fee Collection API | Record fee payments and generate transactions. | High | Pending | BE4-013 | Payment History API | Return complete payment transaction history. | High | Pending | BE4-018 | Report Card API | Generate digital report cards. | High | Pending | BE4-024 | Examination Report API | Generate examination performance reports. | High | Pending | BE4-030 | Announcement API | Manage institute-wide announcements. | Medium | Pending | BE4-036 | Backup Configuration API | Store backup and recovery settings. | Low | Pending | BE4-041 | Examination Analytics API | Return result analysis and subject-wise performance. | High | Pending
BE4-005 | Installment Management API | Manage installment schedules and due dates. | High | Pending | [5 empty] | BE4-019 | Revaluation API | Handle revaluation requests and approvals. | Medium | Pending | BE4-025 | Export API | Export reports to PDF, Excel, and CSV formats. | High | Pending | BE4-031 | WhatsApp Notification API | Prepare future-ready WhatsApp notification integration. | Low | Pending
BE4-006 | Scholarship & Discount API | Apply scholarships, discounts, and concessions. | Medium | Pending
BE4-007 | Refund Management API | Handle fee refund requests and approvals. | Medium | Pending
BE4-008 | Receipt Generation API | Generate downloadable PDF receipts after payment. | High | Pending
Database Architecture
Module Ownership
· Fee Management
· Payment Management
· Examination Management
· Result Management
· Reports & Analytics
· Notifications
· Dashboard Analytics
· Audit Logs
· System Settings
1. Fee Structures Collection
Collection Name
fee_structures
Field | Type | Required | Description
_id | ObjectId | Yes | Primary Key
feeStructureId | String | Yes | Unique Fee Structure ID
courseId | ObjectId | Yes | Reference Course
batchId | ObjectId | Yes | Reference Batch
academicYearId | ObjectId | Yes | Reference Academic Year
tuitionFee | Number | Yes | Tuition Fee
admissionFee | Number | Yes | Admission Fee
examinationFee | Number | Yes | Examination Fee
libraryFee | Number | No | Library Fee
miscellaneousFee | Number | No | Other Charges
totalFee | Number | Yes | Total Amount
installmentAllowed | Boolean | Yes | Installment Option
createdAt | Date | Yes | Timestamp
updatedAt | Date | Yes | Timestamp
2. Student Fees Collection
Collection Name
student_fees
Field | Type
_id | ObjectId
studentId | ObjectId
feeStructureId | ObjectId
totalFee | Number
paidAmount | Number
pendingAmount | Number
discount | Number
scholarship | Number
paymentStatus | String
dueDate | Date
createdAt | Date
3. Payments Collection
Collection Name
payments
Field | Type
_id | ObjectId
paymentId | String
studentId | ObjectId
feeId | ObjectId
transactionId | String
paymentMethod | String
gateway | String
amount | Number
paymentDate | Date
paymentStatus | String
receiptNumber | String
4. Examinations Collection
Collection Name
examinations
Field | Type
_id | ObjectId
examName | String
examType | String
courseId | ObjectId
batchId | ObjectId
academicYearId | ObjectId
examDate | Date
totalMarks | Number
passingMarks | Number
status | String
5. Student Results Collection
Collection Name
student_results
Field | Type
_id | ObjectId
studentId | ObjectId
examinationId | ObjectId
subjectId | ObjectId
marksObtained | Number
totalMarks | Number
grade | String
percentage | Number
GPA | Number
rank | Number
resultStatus | String
6. Report Cards Collection
Collection Name
report_cards
Field | Type
_id | ObjectId
reportCardNumber | String
studentId | ObjectId
examinationId | ObjectId
totalMarks | Number
obtainedMarks | Number
percentage | Number
overallGrade | String
attendancePercentage | Number
generatedDate | Date
pdfUrl | String
7. Notifications Collection
Collection Name
notifications
Field | Type
_id | ObjectId
title | String
message | String
notificationType | String
recipientType | String
recipientId | ObjectId
isRead | Boolean
sentAt | Date
createdBy | ObjectId
8. Announcements Collection
Collection Name
announcements
Field | Type
_id | ObjectId
title | String
description | String
targetAudience | String
branchId | ObjectId
startDate | Date
endDate | Date
createdBy | ObjectId
9. Reports Collection
Collection Name
reports
Field | Type
_id | ObjectId
reportName | String
reportType | String
generatedBy | ObjectId
generatedDate | Date
fileUrl | String
exportFormat | String
10. Dashboard Analytics Collection
Collection Name
dashboard_analytics
Field | Type
_id | ObjectId
reportDate | Date
totalStudents | Number
totalFaculty | Number
totalCourses | Number
totalRevenue | Number
totalPendingFees | Number
attendancePercentage | Number
passPercentage | Number
updatedAt | Date
11. Audit Logs Collection
Collection Name
audit_logs
Field | Type
_id | ObjectId
userId | ObjectId
module | String
action | String
oldValue | Object
newValue | Object
ipAddress | String
browser | String
createdAt | Date
12. Refund Requests Collection
Collection Name
refund_requests
Field | Type
_id | ObjectId
studentId | ObjectId
paymentId | ObjectId
refundAmount | Number
reason | String
status | String
approvedBy | ObjectId
refundDate | Date
Entity Relationship Diagram (ERD)
Courses
│
Batches
│
Fee Structures
│
Student Fees
│
Payments
│
Refund Requests
Students ───────────────┐
│
Examinations
│
Student Results
│
Report Cards
Users
│
├──────── Notifications
├──────── Announcements
├──────── Reports
└──────── Audit Logs
Dashboard Analytics
│
(Data from Fees, Students,
Attendance & Results)

## Sheet1
paths | [5 empty] | # ============================== # Application # ============================== NODE_ENV=development PORT=5000 # ============================== # Frontend URL # ============================== CLIENT_URL=http://localhost:5173 # ============================== # PostgreSQL Database # ============================== DB_HOST=localhost DB_PORT=5432 DB_NAME=college_erp DB_USER=postgres DB_PASSWORD=your_password # Or use a single connection string DATABASE_URL=postgresql://postgres:your_password@localhost:5432/college_erp # ============================== # JWT Authentication # ============================== JWT_SECRET=your_super_secret_jwt_key JWT_EXPIRES_IN=7d JWT_REFRESH_SECRET=your_refresh_secret JWT_REFRESH_EXPIRES_IN=30d # ============================== # Password Hashing # ============================== BCRYPT_SALT_ROUNDS=10 # ============================== # File Upload # ============================== MAX_FILE_SIZE=10485760 UPLOAD_PATH=uploads # ============================== # Cloudinary (Optional) # ============================== CLOUDINARY_CLOUD_NAME=your_cloud_name CLOUDINARY_API_KEY=your_api_key CLOUDINARY_API_SECRET=your_api_secret # ============================== # AWS S3 (Optional) # ============================== AWS_ACCESS_KEY_ID=your_access_key AWS_SECRET_ACCESS_KEY=your_secret_key AWS_REGION=ap-south-1 AWS_BUCKET_NAME=college-erp-files # ============================== # Email (Optional) # ============================== SMTP_HOST=smtp.gmail.com SMTP_PORT=587 SMTP_USER=your_email@gmail.com SMTP_PASS=your_app_password # ============================== # Swagger # ============================== SWAGGER_ENABLED=true # ============================== # Face Recognition (Future) # ============================== FACE_API_URL= FACE_API_KEY= # ============================== # Fingerprint SDK (Future) # ============================== FINGERPRINT_API_URL= FINGERPRINT_API_KEY=
# | Page Name | Route Path | # | Page | URL to type in browser
| Faculty Module (5 pages) |  |  | Faculty Module
1 | Faculty List | /faculty | 1 | Faculty List | http://localhost:5173/faculty
2 | Add Faculty | /faculty/add | 2 | Add Faculty | http://localhost:5173/faculty/add
3 | Faculty Profile | /faculty/profile/:id | 3 | Faculty Profile | http://localhost:5173/faculty/profile/SM-001 (replace ID)
4 | Edit Faculty | /faculty/edit/:id | 4 | Edit Faculty | http://localhost:5173/faculty/edit/SM-001 (replace ID)
5 | Faculty Assignment | /faculty/assign | 5 | Faculty Assignment | http://localhost:5173/faculty/assign
| Timetable Module (7 pages) |  |  | Timetable Module
6 | Timetable Dashboard | /timetable or /schedule | 6 | Timetable Dashboard | http://localhost:5173/timetable
7 | Create Timetable | /timetable/create | 7 | Create Timetable | http://localhost:5173/timetable/create
8 | Edit Timetable | /timetable/edit/:id | 8 | Edit Timetable | http://localhost:5173/timetable/edit/TT-001 (replace ID)
9 | Interactive Calendar | /timetable/calendar | 9 | Interactive Calendar | http://localhost:5173/timetable/calendar
10 | Holiday Management | /holidays | 10 | Holiday Management | http://localhost:5173/holidays
11 | Student Timetable | /student/timetable | 11 | Student Timetable | http://localhost:5173/student/timetable
12 | Faculty Timetable | /faculty/timetable | 12 | Faculty Timetable | http://localhost:5173/faculty/timetable
| Attendance Module (9 pages) |  |  | Attendance Module
13 | Attendance Dashboard | /attendance | 13 | Attendance Dashboard | http://localhost:5173/attendance
14 | Manual Attendance | /attendance/manual | 14 | Manual Attendance | http://localhost:5173/attendance/manual
15 | Face Recognition | /attendance/face-recognition | 15 | Face Recognition | http://localhost:5173/attendance/face-recognition
16 | Fingerprint Attendance | /attendance/fingerprint | 16 | Fingerprint Attendance | http://localhost:5173/attendance/fingerprint
17 | QR Attendance | /attendance/qr | 17 | QR Attendance | http://localhost:5173/attendance/qr
18 | Attendance History | /attendance/history | 18 | Attendance History | http://localhost:5173/attendance/history
19 | Attendance Reports | /attendance/reports | 19 | Attendance Reports | http://localhost:5173/attendance/reports
20 | Attendance Analytics | /attendance/analytics | 20 | Attendance Analytics | http://localhost:5173/attendance/analytics
21 | Correction Management | /attendance/correction | 21 | Correction Management | http://localhost:5173/attendance/correction
| Assignment / Homework Module (6 pages) |  |  | Assignment / Homework Module
22 | Assignment List | /assignments | 22 | Assignment List | http://localhost:5173/assignments
23 | Create Assignment | /assignments/create | 23 | Create Assignment | http://localhost:5173/assignments/create
24 | Homework Management | /homework | 24 | Homework Management | http://localhost:5173/homework
25 | Submissions | /submissions | 25 | Submissions | http://localhost:5173/submissions
26 | Evaluation | /evaluation | 26 | Evaluation | http://localhost:5173/evaluation
27 | Assignment Reminders | /reminders | 27 | Assignment Reminders | http://localhost:5173/reminders
| Study Material Module (6 pages) |  |  | Study Material Module
28 | Study Material Dashboard | /study-materials | 28 | Study Material Dashboard | http://localhost:5173/study-materials
29 | Upload Material | /study-materials/upload | 29 | Upload Material | http://localhost:5173/study-materials/upload
30 | Material Categories | /material-categories | 30 | Material Categories | http://localhost:5173/material-categories
31 | Material Version History | /material-version-history | 31 | Material Version History | http://localhost:5173/material-version-history
32 | Material Preview | /study-materials/preview | 32 | Material Preview | http://localhost:5173/study-materials/preview
33 | Download Center | /download-center | 33 | Download Center | http://localhost:5173/download-center
Total: 33 pages integrated across 5 modules. |  |  | rchitecture Summary
Files created (11): |  |  | Frontend (React + Vite + TypeScript)
src/services/axiosInstance.ts |  |  | ├── 20+ pages in features/
src/services/faculty/facultyApi.ts |  |  | ├── 7 API service files (Axios + JWT interceptor)
src/services/timetable/timetableApi.ts |  |  | ├── React Query hooks (useReactQuery.ts)
src/services/attendance/attendanceApi.ts |  |  | └── 16 shared components
src/services/assignment/assignmentApi.ts
src/services/material/materialApi.ts |  |  | Backend (Express + TypeScript)
src/hooks/useFaculty.ts |  |  | ├── 14 microservice modules
src/hooks/useTimetable.ts |  |  | ├── Prisma ORM → PostgreSQL
src/hooks/useAttendance.ts |  |  | ├── JWT auth (access + refresh tokens)
src/hooks/useAssignment.ts |  |  | ├── Zod validation on all inputs
src/hooks/useMaterial.ts |  |  | └── Standardized response format { success, message, data }
Files modified (1):
src/App.tsx — wrapped app with QueryClientProvider + ToastContainer |  |  | Data Flow:
UI → Service (Axios) → Backend API → Controller → Service → Prisma → PostgreSQL
↑ │
└─────────────────────── API Response ←───────────────────────────────────┘
94 backend endpoints connected to 52 frontend service calls — all verified matching.
33 Prisma models with 18 enums — all models used by services exist in schema.
0 TypeScript errors across both frontend and backend.
Step-by-Step Execution Guide |  |  | Production build succeeds with chunk size warning only (non-critical).
Prerequisites
- Node.js v18+
- PostgreSQL (or use the configured Supabase remote DB)
- Git Bash or PowerShell
1. Install Dependencies
# Backend
cd backend
npm install
Step-by-Step Execution Guide Prerequisites - Node.js v18+ - PostgreSQL (or use the configured Supabase remote DB) - Git Bash or PowerShell 1. Install Dependencies # Backend cd backend npm install # Frontend cd .. npm install 2. Configure Environment Backend (backend/.env) — already configured for a remote Supabase PostgreSQL: NODE_ENV=development PORT=5000 DATABASE_URL=postgresql://postgres:%40cCnanda1411441@db.kwgvocscgumkaylchjtd.supabase.co:5432/postgres JWT_SECRET=super-secret-key-change-in-production JWT_EXPIRES_IN=7000d JWT_REFRESH_SECRET=refresh-secret-key-change-in-production JWT_REFRESH_EXPIRES_IN=30d CORS_ORIGIN=http://localhost:5173 BCRYPT_SALT_ROUNDS=12 RATE_LIMIT_WINDOW_MS=900000 RATE_LIMIT_MAX=100 To skip authentication during testing, add this line: SKIP_AUTH=true Frontend — no .env needed. The API URL defaults to http://localhost:5000/api. To override, create frontend/.env: VITE_API_BASE_URL=http://localhost:5000/api 3. Generate Prisma Client & Push Schema cd backend npx prisma generate npx prisma db push This creates all 33 tables + 18 enums in the PostgreSQL database. 4. Seed Database (Optional — for testing) # Seed admin user (faculty/admin accounts) npm run seed:users # Seed reference data (departments, courses, subjects, batches, classrooms) npm run seed # Seed transactional data (attendance, assignments, homeworks, timetables, etc.) npm run seed:continue 5. Start Backend cd backend npm run dev Server starts at http://localhost:5000. Health check: GET http://localhost:5000/api/health 6. Start Frontend (separate terminal) cd frontend # or just `cd ..` from backend npm run dev Frontend starts at http://localhost:5173. How to Test API Calls Option A: Using PowerShell Invoke-RestMethod # Health check Invoke-RestMethod -Uri "http://localhost:5000/api/health" # Login (with SKIP_AUTH=false) $body = @{ email = "admin@college.edu"; password = "password123" } ¦ ConvertTo-Json $response = Invoke-RestMethod -Uri "http://localhost:5000/api/auth/login" -Method Post -Body $body -ContentType "application/json" $token = $response.data.accessToken # Get faculty list (with auth token) Invoke-RestMethod -Uri "http://localhost:5000/api/faculty?page=1&limit=5" -Headers @{ Authorization = "Bearer $token" } # Get holidays stats Invoke-RestMethod -Uri "http://localhost:5000/api/holidays/stats" -Headers @{ Authorization = "Bearer $token" } Option B: With SKIP_AUTH=true (Simpler Testing) Add SKIP_AUTH=true to backend/.env and restart. Then: # Faculty CRUD (no token needed) Invoke-RestMethod -Uri "http://localhost:5000/api/faculty?page=1&limit=5" # Create faculty $body = @{ firstName = "Test"; lastName = "Faculty"; email = "test@test.com" phone = "9999999999"; gender = "Male"; dateOfBirth = "1990-01-01" employeeId = "EMP-TEST-001"; designation = "Professor" department = "Computer Science"; specialization = @("AI") qualification = @("PhD"); experience = 5; joiningDate = "2020-01-01" employmentType = "permanent"; branch = "Main"; campus = "Main Campus" address = @{}; emergencyContact = @{}; username = "testfaculty" password = "test123" } ¦ ConvertTo-Json Invoke-RestMethod -Uri "http://localhost:5000/api/faculty" -Method Post -Body $body -ContentType "application/json" Option C: Using Postman / Bruno / Insomnia Import these as a collection: Method URL GET http://localhost:5000/api/health POST http://localhost:5000/api/auth/login GET http://localhost:5000/api/faculty?page=1&limit=10 POST http://localhost:5000/api/faculty GET http://localhost:5000/api/faculty/:id PATCH http://localhost:5000/api/faculty/:id DELETE http://localhost:5000/api/faculty/:id GET http://localhost:5000/api/attendance/today GET http://localhost:5000/api/attendance/stats GET http://localhost:5000/api/timetable POST http://localhost:5000/api/timetable GET http://localhost:5000/api/holidays GET http://localhost:5000/api/holidays/stats GET http://localhost:5000/api/assignments GET http://localhost:5000/api/homework GET http://localhost:5000/api/materials GET http://localhost:5000/api/dashboard/admin GET http://localhost:5000/api/dashboard/faculty/:id With SKIP_AUTH=true, no Authorization header needed. With SKIP_AUTH=false, add header: Authorization: Bearer <token>. Incomplete Code Files (List) File src/features/face-recognition/components/CameraPreview.tsx:64 src/features/qr-attendance/components/QRScanner.tsx:64 backend/src/shared/middleware/error-handler.middleware.ts:12 backend/src/modules/auth/auth.controller.ts:37 backend/src/modules/upload/upload.controller.ts:12 backend/src/modules/dashboard/dashboard.service.ts:55 No TODO/FIXME comments, no throw new Error('Not implemented') stubs, no broken imports, no missing exports anywhere in the codebase. What's Not Implemented (Design Decisions / Future Work) - Login page — No frontend UI (backend auth is fully functional with JWT + refresh tokens + bcrypt) - ProtectedRoute component — No route guard wrapper (all pages are accessible) - Cloudinary/S3 — Uploads stored on local filesystem only - Swagger docs — Dependencies installed but not configured - Prisma migrations — Using db push instead of migration history - Unit/integration tests — No test framework configured

## Sheet3
-- WARNING: This schema is for context only and is not meant to be run.
-- Table order and constraints may not be valid for execution.
CREATE TABLE public.subject (
id uuid NOT NULL,
subject_code text NOT NULL,
subject_name text NOT NULL,
department text NOT NULL,
semester integer NOT NULL,
credits integer,
is_deleted boolean NOT NULL DEFAULT false,
deleted_at timestamp without time zone,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT subject_pkey PRIMARY KEY (id)
);
CREATE TABLE public.batch (
id uuid NOT NULL,
batch_name text NOT NULL,
department text NOT NULL,
course text NOT NULL,
semester integer NOT NULL,
academic_year text NOT NULL,
is_deleted boolean NOT NULL DEFAULT false,
deleted_at timestamp without time zone,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT batch_pkey PRIMARY KEY (id)
);
CREATE TABLE public.classroom (
id uuid NOT NULL,
classroom_code text NOT NULL,
building text NOT NULL,
floor integer NOT NULL,
room_number text NOT NULL,
capacity integer,
is_deleted boolean NOT NULL DEFAULT false,
deleted_at timestamp without time zone,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT classroom_pkey PRIMARY KEY (id)
);
CREATE TABLE public.faculty (
id uuid NOT NULL,
faculty_id text NOT NULL,
first_name text NOT NULL,
last_name text NOT NULL,
full_name text NOT NULL,
gender text NOT NULL,
date_of_birth date NOT NULL,
email text NOT NULL,
phone text NOT NULL,
alternate_phone text,
profile_image text,
employee_id text NOT NULL,
designation text NOT NULL,
department text NOT NULL,
specialization ARRAY,
qualification ARRAY,
experience integer NOT NULL,
joining_date date NOT NULL,
employment_type text NOT NULL,
salary numeric,
branch text NOT NULL,
campus text NOT NULL,
address jsonb NOT NULL,
emergency_contact jsonb NOT NULL,
username text NOT NULL,
password text NOT NULL,
role text NOT NULL DEFAULT 'faculty'::text,
permissions ARRAY,
status text NOT NULL DEFAULT 'active'::text,
assigned_courses jsonb NOT NULL DEFAULT '[]'::jsonb,
assigned_subjects jsonb NOT NULL DEFAULT '[]'::jsonb,
assigned_batches jsonb NOT NULL DEFAULT '[]'::jsonb,
assigned_semesters jsonb NOT NULL DEFAULT '[]'::jsonb,
transfer_history jsonb NOT NULL DEFAULT '[]'::jsonb,
is_deleted boolean NOT NULL DEFAULT false,
deleted_at timestamp without time zone,
created_by_id uuid NOT NULL,
updated_by_id uuid NOT NULL,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT faculty_pkey PRIMARY KEY (id),
CONSTRAINT faculty_created_by_id_fkey FOREIGN KEY (created_by_id) REFERENCES public.faculty(id),
CONSTRAINT faculty_updated_by_id_fkey FOREIGN KEY (updated_by_id) REFERENCES public.faculty(id)
);
CREATE TABLE public.attendance (
id uuid NOT NULL,
attendance_code text NOT NULL,
student_id uuid NOT NULL,
faculty_id uuid NOT NULL,
subject_id uuid NOT NULL,
batch_id uuid NOT NULL,
classroom_id uuid NOT NULL,
attendance_date date NOT NULL,
start_time text NOT NULL,
end_time text NOT NULL,
attendance_method USER-DEFINED NOT NULL,
attendance_status USER-DEFINED NOT NULL,
remarks text,
created_by_id uuid NOT NULL,
updated_by_id uuid NOT NULL,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
deleted_at timestamp without time zone,
CONSTRAINT attendance_pkey PRIMARY KEY (id),
CONSTRAINT attendance_student_id_fkey FOREIGN KEY (student_id) REFERENCES public.student(id),
CONSTRAINT attendance_faculty_id_fkey FOREIGN KEY (faculty_id) REFERENCES public.faculty(id),
CONSTRAINT attendance_subject_id_fkey FOREIGN KEY (subject_id) REFERENCES public.subject(id),
CONSTRAINT attendance_batch_id_fkey FOREIGN KEY (batch_id) REFERENCES public.batch(id),
CONSTRAINT attendance_classroom_id_fkey FOREIGN KEY (classroom_id) REFERENCES public.classroom(id),
CONSTRAINT attendance_created_by_id_fkey FOREIGN KEY (created_by_id) REFERENCES public.faculty(id),
CONSTRAINT attendance_updated_by_id_fkey FOREIGN KEY (updated_by_id) REFERENCES public.faculty(id)
);
CREATE TABLE public.timetable (
id uuid NOT NULL,
timetable_id text NOT NULL,
academic_year text NOT NULL,
semester integer NOT NULL,
department text NOT NULL,
course text NOT NULL,
batch text NOT NULL,
section text,
subject text NOT NULL,
subject_code text NOT NULL,
subject_id uuid,
faculty_id uuid NOT NULL,
faculty_name text NOT NULL,
classroom_id uuid NOT NULL,
batch_id uuid,
batch_name text NOT NULL,
building text NOT NULL,
floor integer NOT NULL,
room_number text NOT NULL,
day_of_week text NOT NULL,
start_time text NOT NULL,
end_time text NOT NULL,
duration integer NOT NULL,
status text NOT NULL DEFAULT 'scheduled'::text,
remarks text,
recurring_class boolean NOT NULL DEFAULT false,
recurrence_type text,
recurrence_end_date date,
created_by text NOT NULL,
updated_by text NOT NULL,
is_deleted boolean NOT NULL DEFAULT false,
deleted_at timestamp without time zone,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT timetable_pkey PRIMARY KEY (id),
CONSTRAINT timetable_faculty_id_fkey FOREIGN KEY (faculty_id) REFERENCES public.faculty(id),
CONSTRAINT timetable_subject_id_fkey FOREIGN KEY (subject_id) REFERENCES public.subject(id),
CONSTRAINT timetable_batch_id_fkey FOREIGN KEY (batch_id) REFERENCES public.batch(id),
CONSTRAINT timetable_classroom_id_fkey FOREIGN KEY (classroom_id) REFERENCES public.classroom(id)
);
CREATE TABLE public.faculty_transfer (
id uuid NOT NULL,
faculty_id uuid NOT NULL,
from_branch text NOT NULL,
from_department text NOT NULL,
to_branch text NOT NULL,
to_department text NOT NULL,
transfer_date date NOT NULL,
reason text NOT NULL,
approved_by text,
status text NOT NULL DEFAULT 'pending'::text,
performed_by uuid NOT NULL,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT faculty_transfer_pkey PRIMARY KEY (id),
CONSTRAINT faculty_transfer_faculty_id_fkey FOREIGN KEY (faculty_id) REFERENCES public.faculty(id),
CONSTRAINT faculty_transfer_performed_by_fkey FOREIGN KEY (performed_by) REFERENCES public.faculty(id)
);
CREATE TABLE public.assignment_log (
id uuid NOT NULL,
faculty_id uuid NOT NULL,
action text NOT NULL,
entity_type text NOT NULL,
entity_id text,
entity_name text,
oldValue jsonb,
newValue jsonb,
performed_by uuid NOT NULL,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
CONSTRAINT assignment_log_pkey PRIMARY KEY (id),
CONSTRAINT assignment_log_faculty_id_fkey FOREIGN KEY (faculty_id) REFERENCES public.faculty(id),
CONSTRAINT assignment_log_performed_by_fkey FOREIGN KEY (performed_by) REFERENCES public.faculty(id)
);
CREATE TABLE public.student (
id uuid NOT NULL,
student_id text NOT NULL,
first_name text NOT NULL,
last_name text NOT NULL,
full_name text NOT NULL,
email text NOT NULL,
phone text NOT NULL,
roll_number text NOT NULL,
department text NOT NULL,
course text NOT NULL,
semester integer NOT NULL,
batch text NOT NULL,
batch_id uuid,
section text,
gender text NOT NULL,
date_of_birth date NOT NULL,
address jsonb,
profile_image text,
status text NOT NULL DEFAULT 'active'::text,
is_deleted boolean NOT NULL DEFAULT false,
deleted_at timestamp without time zone,
created_by_id uuid NOT NULL,
updated_by_id uuid NOT NULL,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT student_pkey PRIMARY KEY (id),
CONSTRAINT student_batch_id_fkey FOREIGN KEY (batch_id) REFERENCES public.batch(id),
CONSTRAINT student_created_by_id_fkey FOREIGN KEY (created_by_id) REFERENCES public.faculty(id),
CONSTRAINT student_updated_by_id_fkey FOREIGN KEY (updated_by_id) REFERENCES public.faculty(id)
);
CREATE TABLE public.holiday (
id uuid NOT NULL,
holiday_name text NOT NULL,
holiday_type text NOT NULL,
start_date date NOT NULL,
end_date date NOT NULL,
description text,
applicable_departments ARRAY,
academic_year text,
is_deleted boolean NOT NULL DEFAULT false,
deleted_at timestamp without time zone,
created_by text NOT NULL,
updated_by text NOT NULL,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT holiday_pkey PRIMARY KEY (id)
);
CREATE TABLE public.face_recognition (
id uuid NOT NULL,
session_id text NOT NULL,
student_id uuid NOT NULL,
attendance_id uuid,
confidence double precision NOT NULL DEFAULT 0.0,
recognition_time timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
image_url text,
device_id text,
metadata jsonb DEFAULT '{}'::jsonb,
status USER-DEFINED NOT NULL DEFAULT 'pending'::"RecognitionStatus",
created_by_id uuid NOT NULL,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT face_recognition_pkey PRIMARY KEY (id),
CONSTRAINT face_recognition_student_id_fkey FOREIGN KEY (student_id) REFERENCES public.student(id),
CONSTRAINT face_recognition_attendance_id_fkey FOREIGN KEY (attendance_id) REFERENCES public.attendance(id),
CONSTRAINT face_recognition_created_by_id_fkey FOREIGN KEY (created_by_id) REFERENCES public.faculty(id)
);
CREATE TABLE public.fingerprint_attendance (
id uuid NOT NULL,
session_id text NOT NULL,
fingerprint_id text NOT NULL,
student_id uuid NOT NULL,
attendance_id uuid,
verification_status USER-DEFINED NOT NULL DEFAULT 'pending'::"FingerprintStatus",
recognition_time timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
scanner_id text,
metadata jsonb DEFAULT '{}'::jsonb,
created_by_id uuid NOT NULL,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT fingerprint_attendance_pkey PRIMARY KEY (id),
CONSTRAINT fingerprint_attendance_student_id_fkey FOREIGN KEY (student_id) REFERENCES public.student(id),
CONSTRAINT fingerprint_attendance_attendance_id_fkey FOREIGN KEY (attendance_id) REFERENCES public.attendance(id),
CONSTRAINT fingerprint_attendance_created_by_id_fkey FOREIGN KEY (created_by_id) REFERENCES public.faculty(id)
);
CREATE TABLE public.qr_session (
id uuid NOT NULL,
qr_token text NOT NULL,
faculty_id uuid NOT NULL,
subject_id uuid NOT NULL,
batch_id uuid NOT NULL,
classroom_id uuid NOT NULL,
attendance_date date NOT NULL,
start_time text NOT NULL,
end_time text NOT NULL,
expiry_time timestamp without time zone NOT NULL,
status USER-DEFINED NOT NULL DEFAULT 'active'::"QRStatus",
created_by_id uuid NOT NULL,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT qr_session_pkey PRIMARY KEY (id),
CONSTRAINT qr_session_faculty_id_fkey FOREIGN KEY (faculty_id) REFERENCES public.faculty(id),
CONSTRAINT qr_session_subject_id_fkey FOREIGN KEY (subject_id) REFERENCES public.subject(id),
CONSTRAINT qr_session_batch_id_fkey FOREIGN KEY (batch_id) REFERENCES public.batch(id),
CONSTRAINT qr_session_classroom_id_fkey FOREIGN KEY (classroom_id) REFERENCES public.classroom(id),
CONSTRAINT qr_session_created_by_id_fkey FOREIGN KEY (created_by_id) REFERENCES public.faculty(id)
);
CREATE TABLE public.qr_scan (
id uuid NOT NULL,
qr_session_id uuid NOT NULL,
student_id uuid NOT NULL,
attendance_id uuid,
scanned_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
status USER-DEFINED NOT NULL DEFAULT 'pending'::"QRScanStatus",
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT qr_scan_pkey PRIMARY KEY (id),
CONSTRAINT qr_scan_qr_session_id_fkey FOREIGN KEY (qr_session_id) REFERENCES public.qr_session(id),
CONSTRAINT qr_scan_student_id_fkey FOREIGN KEY (student_id) REFERENCES public.student(id),
CONSTRAINT qr_scan_attendance_id_fkey FOREIGN KEY (attendance_id) REFERENCES public.attendance(id)
);
CREATE TABLE public.attendance_correction (
id uuid NOT NULL,
attendance_id uuid NOT NULL,
student_id uuid NOT NULL,
attendance_date date NOT NULL,
current_status USER-DEFINED NOT NULL,
requested_status USER-DEFINED NOT NULL,
reason text NOT NULL,
attachment_url text,
approval_status USER-DEFINED NOT NULL DEFAULT 'pending'::"CorrectionApprovalStatus",
approved_by_id uuid,
approval_date timestamp without time zone,
created_by_id uuid NOT NULL,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT attendance_correction_pkey PRIMARY KEY (id),
CONSTRAINT attendance_correction_attendance_id_fkey FOREIGN KEY (attendance_id) REFERENCES public.attendance(id),
CONSTRAINT attendance_correction_student_id_fkey FOREIGN KEY (student_id) REFERENCES public.student(id),
CONSTRAINT attendance_correction_approved_by_id_fkey FOREIGN KEY (approved_by_id) REFERENCES public.faculty(id),
CONSTRAINT attendance_correction_created_by_id_fkey FOREIGN KEY (created_by_id) REFERENCES public.faculty(id)
);
CREATE TABLE public.department (
id uuid NOT NULL,
name text NOT NULL,
code text NOT NULL,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT department_pkey PRIMARY KEY (id)
);
CREATE TABLE public.course (
id uuid NOT NULL,
name text NOT NULL,
code text NOT NULL,
duration integer,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT course_pkey PRIMARY KEY (id)
);
CREATE TABLE public.semester (
id uuid NOT NULL,
semester integer NOT NULL,
name text NOT NULL,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT semester_pkey PRIMARY KEY (id)
);
CREATE TABLE public.assignment (
id uuid NOT NULL,
assignment_code text NOT NULL,
title text NOT NULL,
description text,
instructions text,
department_id uuid NOT NULL,
course_id uuid NOT NULL,
semester_id uuid NOT NULL,
subject_id uuid NOT NULL,
batch_id uuid NOT NULL,
faculty_id uuid NOT NULL,
total_marks integer NOT NULL,
passing_marks integer NOT NULL,
publish_date date NOT NULL,
due_date date NOT NULL,
due_time text NOT NULL,
allow_late_submission boolean NOT NULL DEFAULT false,
max_file_size integer,
max_attempts integer DEFAULT 1,
visibility USER-DEFINED NOT NULL DEFAULT 'visible'::"AssignmentVisibility",
status USER-DEFINED NOT NULL DEFAULT 'active'::"AssignmentStatus",
created_by_id uuid NOT NULL,
updated_by_id uuid NOT NULL,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
deleted_at timestamp without time zone,
CONSTRAINT assignment_pkey PRIMARY KEY (id),
CONSTRAINT assignment_department_id_fkey FOREIGN KEY (department_id) REFERENCES public.department(id),
CONSTRAINT assignment_course_id_fkey FOREIGN KEY (course_id) REFERENCES public.course(id),
CONSTRAINT assignment_semester_id_fkey FOREIGN KEY (semester_id) REFERENCES public.semester(id),
CONSTRAINT assignment_subject_id_fkey FOREIGN KEY (subject_id) REFERENCES public.subject(id),
CONSTRAINT assignment_batch_id_fkey FOREIGN KEY (batch_id) REFERENCES public.batch(id),
CONSTRAINT assignment_faculty_id_fkey FOREIGN KEY (faculty_id) REFERENCES public.faculty(id),
CONSTRAINT assignment_created_by_id_fkey FOREIGN KEY (created_by_id) REFERENCES public.faculty(id),
CONSTRAINT assignment_updated_by_id_fkey FOREIGN KEY (updated_by_id) REFERENCES public.faculty(id)
);
CREATE TABLE public.assignment_attachment (
id uuid NOT NULL,
assignment_id uuid NOT NULL,
file_name text NOT NULL,
file_type text NOT NULL,
file_url text NOT NULL,
file_size integer,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
CONSTRAINT assignment_attachment_pkey PRIMARY KEY (id),
CONSTRAINT assignment_attachment_assignment_id_fkey FOREIGN KEY (assignment_id) REFERENCES public.assignment(id)
);
CREATE TABLE public.homework (
id uuid NOT NULL,
title text NOT NULL,
description text,
department_id uuid NOT NULL,
course_id uuid NOT NULL,
batch_id uuid NOT NULL,
subject_id uuid NOT NULL,
faculty_id uuid NOT NULL,
due_date date NOT NULL,
status USER-DEFINED NOT NULL DEFAULT 'active'::"HomeworkStatus",
created_by_id uuid NOT NULL,
updated_by_id uuid NOT NULL,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
deleted_at timestamp without time zone,
CONSTRAINT homework_pkey PRIMARY KEY (id),
CONSTRAINT homework_department_id_fkey FOREIGN KEY (department_id) REFERENCES public.department(id),
CONSTRAINT homework_course_id_fkey FOREIGN KEY (course_id) REFERENCES public.course(id),
CONSTRAINT homework_batch_id_fkey FOREIGN KEY (batch_id) REFERENCES public.batch(id),
CONSTRAINT homework_subject_id_fkey FOREIGN KEY (subject_id) REFERENCES public.subject(id),
CONSTRAINT homework_faculty_id_fkey FOREIGN KEY (faculty_id) REFERENCES public.faculty(id),
CONSTRAINT homework_created_by_id_fkey FOREIGN KEY (created_by_id) REFERENCES public.faculty(id),
CONSTRAINT homework_updated_by_id_fkey FOREIGN KEY (updated_by_id) REFERENCES public.faculty(id)
);
CREATE TABLE public.homework_attachment (
id uuid NOT NULL,
homework_id uuid NOT NULL,
file_name text NOT NULL,
file_type text NOT NULL,
file_url text NOT NULL,
file_size integer,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
CONSTRAINT homework_attachment_pkey PRIMARY KEY (id),
CONSTRAINT homework_attachment_homework_id_fkey FOREIGN KEY (homework_id) REFERENCES public.homework(id)
);
CREATE TABLE public.assignment_submission (
id uuid NOT NULL,
submission_code text NOT NULL,
assignment_id uuid NOT NULL,
student_id uuid NOT NULL,
attempt_number integer NOT NULL DEFAULT 1,
submission_date date NOT NULL,
submission_time text NOT NULL,
status USER-DEFINED NOT NULL DEFAULT 'submitted'::"SubmissionStatus",
remarks text,
late_flag boolean NOT NULL DEFAULT false,
graded_by_id uuid,
graded_at timestamp without time zone,
is_deleted boolean NOT NULL DEFAULT false,
deleted_at timestamp without time zone,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT assignment_submission_pkey PRIMARY KEY (id),
CONSTRAINT assignment_submission_assignment_id_fkey FOREIGN KEY (assignment_id) REFERENCES public.assignment(id),
CONSTRAINT assignment_submission_student_id_fkey FOREIGN KEY (student_id) REFERENCES public.student(id),
CONSTRAINT assignment_submission_graded_by_id_fkey FOREIGN KEY (graded_by_id) REFERENCES public.faculty(id)
);
CREATE TABLE public.submission_attachment (
id uuid NOT NULL,
submission_id uuid NOT NULL,
file_name text NOT NULL,
file_type text NOT NULL,
file_url text NOT NULL,
file_size integer,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
CONSTRAINT submission_attachment_pkey PRIMARY KEY (id),
CONSTRAINT submission_attachment_submission_id_fkey FOREIGN KEY (submission_id) REFERENCES public.assignment_submission(id)
);
CREATE TABLE public.evaluation (
id uuid NOT NULL,
submission_id uuid NOT NULL,
faculty_id uuid NOT NULL,
marks_obtained numeric NOT NULL,
total_marks integer NOT NULL,
grade text NOT NULL,
feedback text,
remarks text,
evaluation_date date NOT NULL,
status USER-DEFINED NOT NULL DEFAULT 'draft'::"EvaluationStatus",
previous_version jsonb,
created_by_id uuid NOT NULL,
updated_by_id uuid NOT NULL,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
deleted_at timestamp without time zone,
CONSTRAINT evaluation_pkey PRIMARY KEY (id),
CONSTRAINT evaluation_submission_id_fkey FOREIGN KEY (submission_id) REFERENCES public.assignment_submission(id),
CONSTRAINT evaluation_faculty_id_fkey FOREIGN KEY (faculty_id) REFERENCES public.faculty(id),
CONSTRAINT evaluation_created_by_id_fkey FOREIGN KEY (created_by_id) REFERENCES public.faculty(id),
CONSTRAINT evaluation_updated_by_id_fkey FOREIGN KEY (updated_by_id) REFERENCES public.faculty(id)
);
CREATE TABLE public.chapter (
id uuid NOT NULL,
chapter_name text NOT NULL,
subject_id uuid NOT NULL,
description text,
chapter_number integer,
is_deleted boolean NOT NULL DEFAULT false,
deleted_at timestamp without time zone,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
CONSTRAINT chapter_pkey PRIMARY KEY (id),
CONSTRAINT chapter_subject_id_fkey FOREIGN KEY (subject_id) REFERENCES public.subject(id)
);
CREATE TABLE public.study_material (
id uuid NOT NULL,
material_code text NOT NULL,
title text NOT NULL,
description text,
department_id uuid NOT NULL,
course_id uuid NOT NULL,
semester_id uuid NOT NULL,
subject_id uuid NOT NULL,
chapter_id uuid,
batch_id uuid NOT NULL,
category_id uuid,
uploaded_by_id uuid NOT NULL,
material_type USER-DEFINED NOT NULL,
visibility USER-DEFINED NOT NULL DEFAULT 'PUBLIC'::"MaterialVisibility",
file_name text NOT NULL,
original_file_name text NOT NULL,
content_hash text,
file_url text NOT NULL,
thumbnail_url text,
file_extension text NOT NULL,
mime_type text NOT NULL,
file_size integer NOT NULL,
total_downloads integer NOT NULL DEFAULT 0,
total_views integer NOT NULL DEFAULT 0,
is_public boolean NOT NULL DEFAULT true,
status text NOT NULL DEFAULT 'active'::text,
created_by text NOT NULL,
updated_by text,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
deleted_at timestamp without time zone,
CONSTRAINT study_material_pkey PRIMARY KEY (id),
CONSTRAINT study_material_department_id_fkey FOREIGN KEY (department_id) REFERENCES public.department(id),
CONSTRAINT study_material_course_id_fkey FOREIGN KEY (course_id) REFERENCES public.course(id),
CONSTRAINT study_material_semester_id_fkey FOREIGN KEY (semester_id) REFERENCES public.semester(id),
CONSTRAINT study_material_subject_id_fkey FOREIGN KEY (subject_id) REFERENCES public.subject(id),
CONSTRAINT study_material_chapter_id_fkey FOREIGN KEY (chapter_id) REFERENCES public.chapter(id),
CONSTRAINT study_material_batch_id_fkey FOREIGN KEY (batch_id) REFERENCES public.batch(id),
CONSTRAINT study_material_category_id_fkey FOREIGN KEY (category_id) REFERENCES public.material_category(id),
CONSTRAINT study_material_uploaded_by_id_fkey FOREIGN KEY (uploaded_by_id) REFERENCES public.faculty(id)
);
CREATE TABLE public.material_category (
id uuid NOT NULL,
category_name text NOT NULL,
description text,
department_id uuid NOT NULL,
course_id uuid,
semester_id uuid,
subject_id uuid,
chapter_id uuid,
batch_id uuid,
parent_id uuid,
created_by text NOT NULL,
updated_by text,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
deleted_at timestamp without time zone,
CONSTRAINT material_category_pkey PRIMARY KEY (id),
CONSTRAINT material_category_department_id_fkey FOREIGN KEY (department_id) REFERENCES public.department(id),
CONSTRAINT material_category_course_id_fkey FOREIGN KEY (course_id) REFERENCES public.course(id),
CONSTRAINT material_category_semester_id_fkey FOREIGN KEY (semester_id) REFERENCES public.semester(id),
CONSTRAINT material_category_subject_id_fkey FOREIGN KEY (subject_id) REFERENCES public.subject(id),
CONSTRAINT material_category_chapter_id_fkey FOREIGN KEY (chapter_id) REFERENCES public.chapter(id),
CONSTRAINT material_category_batch_id_fkey FOREIGN KEY (batch_id) REFERENCES public.batch(id),
CONSTRAINT material_category_parent_id_fkey FOREIGN KEY (parent_id) REFERENCES public.material_category(id)
);
CREATE TABLE public.material_attachment (
id uuid NOT NULL,
study_material_id uuid NOT NULL,
file_name text NOT NULL,
file_url text NOT NULL,
file_size integer,
file_type text NOT NULL,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
CONSTRAINT material_attachment_pkey PRIMARY KEY (id),
CONSTRAINT material_attachment_study_material_id_fkey FOREIGN KEY (study_material_id) REFERENCES public.study_material(id)
);
CREATE TABLE public.material_download (
id uuid NOT NULL,
study_material_id uuid NOT NULL,
downloaded_by_id text NOT NULL,
downloaded_by_role text NOT NULL,
downloaded_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
ip_address text,
device_info text,
user_agent text,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
CONSTRAINT material_download_pkey PRIMARY KEY (id),
CONSTRAINT material_download_study_material_id_fkey FOREIGN KEY (study_material_id) REFERENCES public.study_material(id)
);
CREATE TABLE public.material_search_log (
id uuid NOT NULL,
user_id text NOT NULL,
query text NOT NULL,
filters jsonb DEFAULT '{}'::jsonb,
result_count integer,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
CONSTRAINT material_search_log_pkey PRIMARY KEY (id)
);
CREATE TABLE public.assignment_reminder (
id uuid NOT NULL,
assignment_id uuid NOT NULL,
student_id uuid,
reminder_date date NOT NULL,
reminder_time text NOT NULL,
reminder_type USER-DEFINED NOT NULL DEFAULT 'upcoming_deadline'::"ReminderType",
status USER-DEFINED NOT NULL DEFAULT 'pending'::"ReminderStatus",
notification_channel USER-DEFINED NOT NULL DEFAULT 'email'::"NotificationChannel",
frequency USER-DEFINED NOT NULL DEFAULT 'once'::"ReminderFrequency",
custom_cron_expression text,
sent_at timestamp without time zone,
error_message text,
metadata jsonb DEFAULT '{}'::jsonb,
created_by_id uuid NOT NULL,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
deleted_at timestamp without time zone,
CONSTRAINT assignment_reminder_pkey PRIMARY KEY (id),
CONSTRAINT assignment_reminder_assignment_id_fkey FOREIGN KEY (assignment_id) REFERENCES public.assignment(id),
CONSTRAINT assignment_reminder_student_id_fkey FOREIGN KEY (student_id) REFERENCES public.student(id),
CONSTRAINT assignment_reminder_created_by_id_fkey FOREIGN KEY (created_by_id) REFERENCES public.faculty(id)
);
CREATE TABLE public.upload (
id uuid NOT NULL,
original_name text NOT NULL,
file_name text NOT NULL,
mime_type text NOT NULL,
extension text NOT NULL,
size integer NOT NULL,
url text NOT NULL,
provider text NOT NULL DEFAULT 'local'::text,
thumbnail_url text,
content_hash text,
uploaded_by_id text,
uploaded_by_role text,
module text,
module_id text,
metadata jsonb DEFAULT '{}'::jsonb,
created_at timestamp without time zone NOT NULL DEFAULT CURRENT_TIMESTAMP,
updated_at timestamp without time zone NOT NULL,
deleted_at timestamp without time zone,
CONSTRAINT upload_pkey PRIMARY KEY (id)
);